## Dashboard
Ghar Sajag — P0 Engineering Progress
Evidence-backed status as of 2026-09-08. Green means the named checkpoint passed; it does not mean the physical product or pilot is complete.
P0 requirements |  | Logical modules |  | Host-verified modules |  | Pilot-complete modules
24 |  | 32 |  | 30 |  | 0
Completion by checkpoint phase
Phase | Scope | Complete / passed | Partial | Pending | Completion | Status | What the number means
Design | 64 | 64 | 0 | 0 | 100% | Complete | HLD and LLD checkpoints across 32 modules
Host baseline | 64 | 60 | 4 | 0 | 93.75% | In Progress | Host code plus host verification checkpoints
Target integration | 32 | 0 | 0 | 32 | 0% | Not Started | ESP-IDF hardware or production provider/database integration
Field / E2E | 32 | 0 | 0 | 32 | 0% | Not Started | Real devices, phones, outages and installed-home evidence
Current conclusion
The architecture is implemented beyond paper: every module has host-executable logic or an explicit adapter seam, and the host suite is green. The system is still not a working physical prototype, pilot-ready product, or commercial release. The next gate is one real PIR → ESP32-C3 → ESP-NOW → hub journal → local dashboard vertical slice.
Next ordered gates
Priority | Gate | Status | Exit evidence | Priority | Gate | Status | Exit evidence
1 | ESP-IDF skeleton + board profiles | Not Started | C3 and hub compile, flash and report boot/version | 2 | One PIR vertical slice | Not Started | One event appears once with original time
3 | Local routine + resident controls | Not Started | Online/offline/privacy/away flows pass | 4 | Production caregiver path | Not Started | Primary/backup phones pass TEST workflow
Status legend
Complete | Named deliverable exists | Passed | Named test passed | Partial | Scaffold/seam exists | Not Started | No target evidence yet
Pending | Target gate not run | In Progress | Some checkpoints remain | Blocked | Cannot proceed | Failed | Named check did not pass

## P0 Requirements
P0 Requirement Traceability
All 24 P0 requirements mapped to owning modules and separated into design, host, target-integration and field gates.
Editable status columns use the shared color legend. Do not mark Overall P0 complete until target and end-to-end evidence exists.
ID | Requirement | Owner modules | HLD | LLD | Host baseline | Target integration | End-to-end | Overall P0 | Current evidence | Next exit gate
F01 | Household profile and caregiver roles | B01, B02, A01, S01 | Complete | Complete | Complete | Pending | Pending | In Progress | Mapped host modules implemented and verified where applicable: B01, B02, A01, S01. | Bind household/roles to durable PostgreSQL + OIDC and test tenant isolation.
F02 | Resident consent and privacy controls | B02, H06, H07, A01, B08 | Complete | Complete | Complete | Pending | Pending | In Progress | Mapped host modules implemented and verified where applicable: B02, H06, H07, A01, B08. | Bind privacy switch and consent withdrawal end to end; verify resident comprehension.
F03 | Kit provisioning and installation verification | N04, H07, B06, A01, S03, T02 | Complete | Complete | Partial | Pending | Pending | In Progress | Provisioning/install domain gates and HIL plan exist; no board provisioning or installed-kit evidence. | Compile/flash both boards; perform claim, input, control and TEST-delivery installation checks.
F04 | Configurable morning routine | A03, B06, H07, H03, H05, S02 | Complete | Complete | Complete | Pending | Pending | In Progress | Mapped host modules implemented and verified where applicable: A03, B06, H07, H03, H05, S02. | Persist configuration, deliver to hub, apply atomically and test timezone/window boundaries.
F05 | Morning activity evidence | N01, H01, H02, H05, S02, B07, A02 | Complete | Complete | Complete | Pending | Pending | In Progress | Mapped host modules implemented and verified where applicable: N01, H01, H02, H05, S02, B07, A02. | Run AM312 PIR → C3 → ESP-NOW → hub journal → dashboard vertical slice.
F06 | Explicit I’m OK check-in | H06, H02, H05, S02, B07, A02 | Complete | Complete | Complete | Pending | Pending | In Progress | Mapped host modules implemented and verified where applicable: H06, H02, H05, S02, B07, A02. | Wire I'm OK button and verify saved-local / remotely-accepted feedback while offline and online.
F07 | Call family request | H06, H02, H05, B04, B05, A04 | Complete | Complete | Complete | Pending | Pending | In Progress | Mapped host modules implemented and verified where applicable: H06, H02, H05, B04, B05, A04. | Wire Call family button and verify durable escalation plus primary/backup phone delivery.
F08 | Missing morning activity workflow | H03, H04, H05, S02, B04, B05 | Complete | Complete | Complete | Pending | Pending | In Progress | Mapped host modules implemented and verified where applicable: H03, H04, H05, S02, B04, B05. | Run covered, unknown-coverage, privacy, away and missing-activity scenarios on target hardware.
F09 | Main-door history and quiet notice | N01, H05, S02, B07, B05, A02 | Complete | Complete | Complete | Pending | Pending | In Progress | Mapped host modules implemented and verified where applicable: N01, H05, S02, B07, B05, A02. | Wire reed sensor, tune door events and validate opt-in quiet notification on real phones.
F10 | Away, pause and visitor modes | A03, B02, H07, H06, H05, S02 | Complete | Complete | Complete | Pending | Pending | In Progress | Mapped host modules implemented and verified where applicable: A03, B02, H07, H06, H05, S02. | Integrate away/pause/visitor controls and verify no false reassurance or stale state.
F11 | Caregiver dashboard and timeline | B07, B08, A02, A05 | Complete | Complete | Complete | Pending | Pending | In Progress | Mapped host modules implemented and verified where applicable: B07, B08, A02, A05. | Connect production PWA to authenticated API; validate freshness and accessibility on supported phones.
F12 | Acknowledgement and resolution | B04, B07, B05, A04, H08 | Complete | Complete | Complete | Pending | Pending | In Progress | Mapped host modules implemented and verified where applicable: B04, B07, B05, A04, H08. | Verify claim, acknowledgement and resolution against durable concurrent storage.
F13 | Backup routing and delivery visibility | B05, B04, B08, A04, A05 | Complete | Complete | Complete | Pending | Pending | In Progress | Mapped host modules implemented and verified where applicable: B05, B04, B08, A04, A05. | Integrate Web Push and worker leases; test primary failure, backup route and delivery-state clarity.
F14 | Opt-in daily morning summary | B05, B07, A03, A02 | Complete | Complete | Complete | Pending | Pending | In Progress | Mapped host modules implemented and verified where applicable: B05, B07, A03, A02. | Schedule one opt-in summary from durable projections and verify coverage-honest wording.
E01 | Node health, battery and coverage | N03, N02, H04, B08, A02 | Complete | Complete | Complete | Pending | Pending | In Progress | Mapped host modules implemented and verified where applicable: N03, N02, H04, B08, A02. | Measure node voltage/current, RF contact lease, sensor faults and installed battery behavior.
E02 | Reliable transport and duplicate handling | N02, N05, H01, H02, H08, B03, S01 | Complete | Complete | Complete | Pending | Pending | In Progress | Mapped host modules implemented and verified where applicable: N02, N05, H01, H02, H08, B03, S01. | Bind ESP-NOW and MQTT/TLS; inject loss, duplicates, resets and replay across real devices.
E03 | Local operation during internet failure | H03, H04, H05, H06, H02, H08 | Complete | Complete | Complete | Pending | Pending | In Progress | Mapped host modules implemented and verified where applicable: H03, H04, H05, H06, H02, H08. | Pass 72-hour WAN outage with local operation, bounded storage and exactly-once replay effects.
E04 | Hub/cloud/app connectivity and freshness | H08, B08, B07, A05, A02 | Complete | Complete | Complete | Pending | Pending | In Progress | Mapped host modules implemented and verified where applicable: H08, B08, B07, A05, A02. | Expose independent hub/cloud/app freshness using real broker, API, push and phones.
E05 | Persistence, recovery and bounded storage | N05, H02, B03, B04, B05, B08 | Complete | Complete | Complete | Pending | Pending | In Progress | Mapped host modules implemented and verified where applicable: N05, H02, B03, B04, B05, B08. | Implement flash journal + PostgreSQL durability; pass interrupted-write and restore tests.
E06 | Trusted time and boundary handling | H03, H07, H05, S01, S02 | Complete | Complete | Complete | Pending | Pending | In Progress | Mapped host modules implemented and verified where applicable: H03, H07, H05, S01, S02. | Bind authenticated time; test reboot, drift, expiry and timezone/DST boundaries.
E07 | Versioned configuration and atomic application | B06, A03, H07, N04, H08, S01 | Complete | Complete | Complete | Pending | Pending | In Progress | Mapped host modules implemented and verified where applicable: B06, A03, H07, N04, H08, S01. | Bind NVS and cloud config delivery; pass atomic apply, reboot restore, stale and rollback cases.
E08 | Security, privacy and tenant isolation | S03, B01, B02, B06, B08, A05, T01 | Complete | Complete | Complete | Pending | Pending | In Progress | Mapped host modules implemented and verified where applicable: S03, B01, B02, B06, B08, A05, T01. | Integrate OIDC, TLS, ACL/RLS, secret storage and privacy/security review evidence.
E09 | Signed firmware update and recovery | S03, H07, N04, B06, B08, T02 | Complete | Complete | Partial | Pending | Pending | In Progress | Fail-closed update policy seam and rollback checks exist; no real signature, secure boot or OTA recovery. | Implement real SHA-256/signature verification, secure boot, signed OTA and recovery drill.
E10 | Verification, observability and release evidence | B08, A02, T01, T02, T03, H02, H08 | Complete | Complete | Partial | Pending | Pending | In Progress | Host suite is green; hardware, RF, power, provider and installed-home evidence are still missing. | Add CI, HIL, RF/current/power, staging/provider and four-node installed-home evidence bundle.

## HLD Overview
High-Level Design and Runtime Ownership
System layers, communication boundaries and the proposed hub FreeRTOS binding. Design is complete; target binding remains pending.
Architecture layers
Layer | Modules | Primary responsibility | Runtime / owner | Communication | Durable or owned state | Host state | Remaining target gate
Node firmware | N01–N05 | Qualify PIR/reed/button evidence; retain and retry events; manage node power/config | ESP32-C3 node; NodeRuntime owns composition | GPIO/ADC locally; planned ESP-NOW to hub | Bounded retained-event store and active node config | Complete | GPIO, deep sleep, ADC, ESP-NOW, NVS/flash and current/RF qualification
Hub firmware | H01–H08 | Persist evidence, track coverage/time, run deterministic routines, resident actions and cloud replay | ESP32 DevKit V1; one state-owner task plus adapters | ESP-NOW from nodes; local GPIO/I2C; planned MQTT/TLS to backend | Hub journal, routine state, coverage, config and cloud outbox | Complete | ESP-IDF/FreeRTOS binding, flash journal, controls, Wi-Fi/MQTT/TLS and reset tests
Backend | B01–B08 | Tenant/consent, idempotent ingest, incidents, notifications, fleet config, queries and audit | Python domain services; production workers/API pending | MQTT/TLS, HTTPS/JSON, Web Push | Durable home, event, incident, outbox and audit data | Complete | PostgreSQL/RLS, OIDC, MQTT consumer, worker leases, push provider, backup/restore
Caregiver app | A01–A05 | Onboarding, evidence/freshness view, routine settings, incident actions and offline/cache policy | Responsive browser/PWA baseline | HTTPS/JSON, optional SSE/Web Push | Versioned local cache only; server remains authoritative | Complete | Production framework/API/OIDC integration, IndexedDB/push, accessibility, localization, phones
Shared | S01–S03 | Versioned contracts, deterministic rules and fail-closed update/security policy | Portable schemas and C++ core | Schemas/OpenAPI across layers; injected crypto seam | Versioned schema/config identities; caller-owned rule state | Complete | Generated bindings/golden vectors, protected keys, real crypto, secure boot and signed OTA
Test / Ops | T01–T03 | Host verification, HIL planning and example deployment/operations | Host runner plus pending physical/staging lanes | CLI, serial/instrument adapters, deployment configs | Fixtures, evidence reports and external service state | Partial | CI service, physical fault/current/RF tests, staging, restore drill and installed-home evidence
Proposed hub FreeRTOS binding
Task / adapter | Priority intent | Consumes | Produces | Owns mutable state | Blocking rule | Design status | Target status
radio_rx adapter | High / callback bounded | Authenticated ESP-NOW frame | Fixed-value ingress mailbox item | No domain state | Copy/validate/enqueue only; never flash or run rules in callback | Complete | Pending
state_core task | Single domain owner | Ingress, UI commands, deadlines, config | Journal commits, ACK class, routine/coverage decisions | H02–H07 state snapshots | Serializes domain mutation; no network blocking | Complete | Pending
local_ui task | Responsive resident feedback | Button/switch events and feedback command | GPIO/display/buzzer effects | Physical debounce only | Never decides incident state | Complete | Pending
cloud_sync task | Backoff-aware | H02 committed outbox | MQTT/TLS publish and application ACK command | Connection/retry state only | Transport ACK never retires business evidence | Complete | Pending
supervisor/timer task | Periodic health | Monotonic clock, task liveness and deadlines | Deadline/health commands | Watchdog counters | No direct mutation of journal/routine state | Complete | Pending
Non-negotiable architecture rules
Rule | Principle |  | Meaning
1 | Durability before ACK |  | Node receives DURABLE only after hub journal commit
2 | Coverage honesty |  | Unknown/offline coverage suppresses missing-activity claims
3 | Separate states |  | Provider acceptance, phone receipt, human ACK and resolution remain distinct
4 | Privacy |  | P0 has no indoor camera, microphone or resident identity inference
5 | Local first |  | Resident controls and routine logic remain useful during WAN failure
6 | One state owner |  | Hub domain mutation is serialized through the state task
7 | Version everything |  | Events, configs and contracts carry stable identity/version
8 | Fail closed |  | Unknown time, coverage or signature never becomes reassurance

## Module Status
Module Implementation Status
32 logical modules. Green is limited to delivered design, host code or verified host tests; every target-integration and field gate is still open.
Status cells are editable. Update only when the stated evidence/exit criterion is available; the dashboard recalculates automatically.
ID | Layer | Module | HLD | LLD | Host code | Host verification | Target integration | Field / E2E | Overall P0 | Current evidence | Remaining gate
N01 | Node firmware | Node sensing | Complete | Complete | Complete | Passed | Pending | Pending | In Progress | Portable C++ host implementation; tests/cpp/test_main.cpp: initial, bounce and stable-rise checks. | Host behavior passes; hardware exit requires voltage, warm-up, hold-time, wake-loop and placement tests.
N02 | Node firmware | Node radio | Complete | Complete | Complete | Passed | Pending | Pending | In Progress | Portable C++ host implementation; C++ tests cover immediate send, volatile ACK retention and durable retirement. | Host retry/ACK semantics pass; ESP-NOW encryption, channel search, callback timing and loss tests remain.
N03 | Node firmware | Node power | Complete | Complete | Complete | Passed | Pending | Pending | In Progress | Portable C++ host implementation; C++ tests verify low/unknown bands and retry wake plan. | Logic passes; ADC calibration, divider leakage, charge status and full current profile require hardware.
N04 | Node firmware | Node lifecycle | Complete | Complete | Complete | Passed | Pending | Pending | In Progress | Portable C++ host implementation; C++ tests cover invalid capability, valid apply, rollback and 120-second window. | Host state transition passes; NVS atomicity, USB jig and authenticated boot registration remain.
N05 | Node firmware | Node storage | Complete | Complete | Complete | Passed | Pending | Pending | In Progress | Portable C++ host implementation; C++ tests cover persist-before-send and ACK class behavior; NodeRuntime composition tested. | Host semantics pass; CRC/commit-marker flash ring and interrupted-write recovery require board partitions.
H01 | Hub firmware | Hub ingest | Complete | Complete | Complete | Passed | Pending | Pending | In Progress | Portable C++ host implementation; C++ tests cover known/unknown peer and callback-to-worker copy. | Host admission passes; frame authentication, payload bounds and ISR/callback latency remain on ESP-IDF.
H02 | Hub firmware | Hub persistence | Complete | Complete | Complete | Passed | Pending | Pending | In Progress | Portable C++ host implementation; C++ tests cover store, duplicate, pending outbox and application ACK. | Host invariants pass; append-only flash record, CRC, checkpoint, wear and 100-cycle crash test remain.
H03 | Hub firmware | Hub time | Complete | Complete | Complete | Passed | Pending | Pending | In Progress | Portable C++ host implementation; C++ tests verify unanchored suppression and trusted bounded estimate. | Host math passes; authenticated exchange, reboot lower-bound and optional RTC behavior remain.
H04 | Hub firmware | Hub coverage | Complete | Complete | Complete | Passed | Pending | Pending | In Progress | Portable C++ host implementation; C++ tests cover never-seen, fresh and 190-second expired lease. | Current-state host logic passes; interval reconstruction and physical sensor-path drills remain.
H05 | Hub firmware | Hub rules adapter | Complete | Complete | Complete | Passed | Pending | Pending | In Progress | Portable C++ host implementation; C++ tests cover evidence, missing, duplicate deadline, coverage unknown and privacy. | Rule paths pass; full scenario replay and long-running device timer/reboot tests remain.
H06 | Hub firmware | Hub resident interface | Complete | Complete | Complete | Passed | Pending | Pending | In Progress | Portable C++ host implementation; C++ tests verify Call family event and offline wording. | Host event/feedback contract passes; buttons, latching switch, OLED/LED, audio load and resident usability remain.
H07 | Hub firmware | Hub lifecycle/config | Complete | Complete | Complete | Passed | Pending | Pending | In Progress | Portable C++ host implementation; C++ tests cover valid apply and stale-version rejection. | Host atomic snapshot passes; NVS transaction, reboot restore, provisioning and OTA binding remain.
H08 | Hub firmware | Hub cloud link | Complete | Complete | Complete | Passed | Pending | Pending | In Progress | Portable C++ host implementation; C++ tests cover urgent ordering and application-level retirement; simulator replays one offline record. | Host scheduling passes; Wi-Fi/TLS/MQTT, ACL, broker failure and 72-hour field replay remain.
B01 | Backend | Identity/access | Complete | Complete | Complete | Passed | Pending | Pending | In Progress | Host domain implementation plus Python tests; test_B01_F01_membership_is_tenant_scoped. | Domain policy passes; production OIDC verification, token audience/issuer and database row-level controls remain.
B02 | Backend | Home/consent | Complete | Complete | Complete | Passed | Pending | Pending | In Progress | Host domain implementation plus Python tests; F01 role test and test_B02_consent_withdrawal_enters_privacy. | Domain state passes; invitation tokens, durable repository and deletion workflow remain.
B03 | Backend | Event ingestion | Complete | Complete | Complete | Passed | Pending | Pending | In Progress | Host domain implementation plus Python tests; test_B03_ingest_is_idempotent. | Domain idempotency passes; PostgreSQL transaction/outbox, MQTT consumer and commit ACK adapter remain.
B04 | Backend | Incident workflow | Complete | Complete | Complete | Passed | Pending | Pending | In Progress | Host domain implementation plus Python tests; call idempotency and test_B04_claim_lease_prevents_double_ownership. | State machine passes; database compare-and-set, HANDOFF_TO_BACKUP and concurrency load tests remain.
B05 | Backend | Notification routing | Complete | Complete | Complete | Passed | Pending | Pending | In Progress | Host domain implementation plus Python tests; B04/B05 route tests, F09 notice test, F14 summary test and TEST exclusion. | Domain routing passes; real Web Push, worker lease, retry/jitter and phone delivery tests remain.
B06 | Backend | Fleet/config | Complete | Complete | Complete | Passed | Pending | Pending | In Progress | Host domain implementation plus Python tests; test_B06_config_version_and_device_binding. | Version semantics pass; PostgreSQL, one-use claim, signed manifest publication and cohort rollout remain.
B07 | Backend | Read models/API | Complete | Complete | Complete | Passed | Pending | Pending | In Progress | Host domain implementation plus Python tests; test_B07_B08_snapshot_separates_activity_from_reachability. | Projection logic passes; pagination, SSE, OpenAPI conformance and React integration remain.
B08 | Backend | Operations/data | Complete | Complete | Complete | Passed | Pending | Pending | In Progress | Host domain implementation plus Python tests; B07/B08 snapshot test and diagnostics assertions. | Host observability passes; PostgreSQL retention/export, independent uptime and restore drill remain.
A01 | Caregiver app | App onboarding | Complete | Complete | Complete | Passed | Pending | Pending | In Progress | Framework-neutral browser logic plus Node tests; Node tests: onboarding validation and installation gate. | Domain/UI model passes; React form, QR claim, accessibility and real phone workflow remain.
A02 | Caregiver app | App home | Complete | Complete | Complete | Passed | Pending | Pending | In Progress | Framework-neutral browser logic plus Node tests; Home-view separation test; static responsive prototype included. | View-model tests pass; React/PWA accessibility, localization and supported-phone tests remain.
A03 | Caregiver app | App routines | Complete | Complete | Complete | Passed | Pending | Pending | In Progress | Framework-neutral browser logic plus Node tests; Routine command and desired/applied status test. | Pure UI logic passes; screen, timezone boundary preview and backend persistence remain.
A04 | Caregiver app | App incidents | Complete | Complete | Complete | Passed | Pending | Pending | In Progress | Framework-neutral browser logic plus Node tests; Incident ownership/action and command-path test. | View/action rules pass; optimistic-pending UI, SSE reconciliation and caregiver comprehension remain.
A05 | Caregiver app | App platform | Complete | Complete | Complete | Passed | Pending | Pending | In Progress | Framework-neutral browser logic plus Node tests; Cache and push capability test. | Framework-neutral adapter passes; OIDC SDK, service worker push handler, IndexedDB and real browser tests remain.
S01 | Shared | Shared contracts | Complete | Complete | Complete | Passed | Pending | Pending | In Progress | Three JSON schemas and OpenAPI surface pass contract verification. | Source contracts pass; CBOR CDDL/generated C++/Python/TypeScript bindings and golden vectors remain.
S02 | Shared | Deterministic rules core | Complete | Complete | Complete | Passed | Pending | Pending | In Progress | Portable C++ host implementation; C++ rule tests and HubRuntime composition. | Host reducer passes; scenario-property, reorder and reboot checkpoint tests remain.
S03 | Shared | Firmware security/update | Complete | Complete | Complete | Passed | Pending | Pending | In Progress | Portable C++ host implementation; C++ tests cover install, rollback, revoke and manifest policy. | Policy passes; protected NVS/secure element, real SHA-256/ECDSA, secure boot and rollback recovery remain.
T01 | Test / Ops | Simulation/CI | Complete | Complete | Complete | Passed | Pending | Pending | In Progress | make verify passed on 2026-09-08: contracts, strict C++17, simulator, Python and Node suites. | Current host suite green; add CI runner, fuzz/property tests and coverage thresholds.
T02 | Test / Ops | Hardware-in-loop tools | Complete | Complete | Partial | Partial | Pending | Pending | In Progress | HIL-safe planning and measurement scaffolding exists; no physical run evidence yet. | Host tooling exists; serial adapter, fault injector, power instrument and installed-home run are required.
T03 | Test / Ops | Deployment/operations | Complete | Complete | Partial | Partial | Pending | Pending | In Progress | Deployment, broker, alert and runbook examples exist; no live staging evidence yet. | Examples complete; staging deployment, secret store, migrations, external monitoring and restore evidence remain.

## LLD Interfaces
Low-Level Design — Interfaces and State
Source paths, public interface, owned state and I/O boundary for every logical module.
ID | Layer | Module | Source files | API / public surface | Owned state | Inputs → outputs | LLD status
N01 | Node firmware | Node sensing | firmware/node/components/sensing/sensing.hpp, sensing.cpp | QualifiedInput::sample(raw_level, now_ms); stable_level() | raw/stable level, edge timestamp, debounce and retrigger clocks | Raw PIR/reed level → optional qualified Motion/DoorOpen/DoorClosed event kind | Complete
N02 | Node firmware | Node radio | firmware/node/components/radio/node_radio.hpp, node_radio.cpp | enqueue(); next_due(); record_transport_result(); apply_ack() | bounded PendingTx deque, attempt count and next-attempt deadline | DomainEvent + application ACK → scheduled transmissions / retired entries | Complete
N03 | Node firmware | Node power | firmware/node/components/power/power.hpp, power.cpp | PowerPolicy::classify(); PowerPolicy::plan() | No mutable ownership; thresholds are explicit policy inputs/constants | Calibrated millivolts + pending work + NodeConfig → BatteryReading and SleepPlan | Complete
N04 | Node firmware | Node lifecycle | firmware/node/components/lifecycle/lifecycle.hpp, lifecycle.cpp | LifecycleService::apply(); open_service_window(); service_window_open() | active NodeConfig and physical-service-window deadline | Versioned NodeConfig / physical action → atomic applied config or reason | Complete
N05 | Node firmware | Node storage | firmware/node/components/storage/node_store.hpp, node_store.cpp | NodeStore::append(); acknowledge(); oldest() | bounded business-event deque and explicit gap-marker flag | Business DomainEvent + ACK → retained/released event or overflow signal | Complete
H01 | Hub firmware | Hub ingest | firmware/hub/components/ingest/ingest.hpp, ingest.cpp | PeerRegistry::authorize/accepts; IngestQueue::callback_copy/pop | authorized source→session map, bounded ingress deque and rejection count | Radio callback DomainEvent → admitted fixed-value mailbox entry | Complete
H02 | Hub firmware | Hub persistence | firmware/hub/components/storage/journal.hpp, journal.cpp | HubJournal::commit(); pending_cloud(); acknowledge_cloud(); contains() | bounded ordered records, event-ID set and application-ACK set | DomainEvent → Stored/Duplicate/Full; committed records → cloud outbox batch | Complete
H03 | Hub firmware | Hub time | firmware/hub/components/time/clock.hpp, clock.cpp | TrustedClock::anchor(); estimate(); valid_for_absence() | trusted server anchor, monotonic anchor and uncertainty | Authenticated time anchor + monotonic now → earliest/latest wall-time estimate and trust | Complete
H04 | Hub firmware | Hub coverage | firmware/hub/components/coverage/coverage.hpp, coverage.cpp | require_node(); observe(); set_sensor_fault(); current(); reasons() | required-node set and per-node last contact, battery and fault | Heartbeat/business contact + lease clock → Covered/Unknown/Fault and reason list | Complete
H05 | Hub firmware | Hub rules adapter | firmware/hub/components/rules/routine_service.hpp, routine_service.cpp | start_window(); set_coverage(); apply(); deadline() | one RoutineConfig and RoutineState owned by the hub state task | Committed event / deadline / coverage → evidence state or stable incident decision | Complete
H06 | Hub firmware | Hub resident interface | firmware/hub/components/ui/resident_ui.hpp, resident_ui.cpp | ResidentUi::make_action(); feedback_for() | Stateless command builder; physical debounce belongs to GPIO adapter | OK/Call/Privacy action → durable DomainEvent and local feedback code/text | Complete
H07 | Hub firmware | Hub lifecycle/config | firmware/hub/components/lifecycle/config_service.hpp, config_service.cpp | ConfigService::apply(); active() | active immutable HomeConfig snapshot and applied version | Desired HomeConfig → applied version or rejection reason | Complete
H08 | Hub firmware | Hub cloud link | firmware/hub/components/cloud/cloud_sync.hpp, cloud_sync.cpp | set_connected(); next_batch(); application_commit_ack(); record_failure() | connection flag, failure count and retry-after deadline; journal owns payload | Committed outbox + connection/ACK → prioritized batch and retirement | Complete
B01 | Backend | Identity/access | backend/ghar_sajag/identity.py | IdentityService.grant/revoke/require | Membership rows keyed by (home_id, actor_id), active flag and expiry | Verified actor claim + home + permission → membership or AuthorizationError | Complete
B02 | Backend | Home/consent | backend/ghar_sajag/homes.py | HomeService.create/set_caregivers/set_mode/withdraw_resident_consent | Home, resident consents, caregiver route, mode and version | Owner commands → validated home/configuration changes and audit | Complete
B03 | Backend | Event ingestion | backend/ghar_sajag/ingest.py | IngestService.accept() | CloudEvent dictionary keyed by (home_id, event_id) | Validated CloudEvent → (stored event, duplicate flag) | Complete
B04 | Backend | Incident workflow | backend/ghar_sajag/incidents.py | IncidentService.create/claim/acknowledge/resolve | Incident plus stable-key index, owner and lease | Hub incident intent / caregiver command → idempotent incident transition | Complete
B05 | Backend | Notification routing | backend/ghar_sajag/notifications.py | schedule_for_incident(); due(); provider_result(); human_acknowledged(); create_door_notice(); build_daily_summary() | unique stage jobs, provider state, advisory notices and one-per-day summary keys | Incident/event/window projection → primary/backup jobs, opt-in advisory or summary | Complete
B06 | Backend | Fleet/config | backend/ghar_sajag/fleet.py | register_device(); publish_config(); record_applied() | device registry and latest desired/applied configuration | Owner/install command or hub ACK → device/config version state | Complete
B07 | Backend | Read models/API | backend/ghar_sajag/queries.py, http_api.py | QueryService.snapshot/timeline; JsonApi.dispatch/WSGI | Derived view only; source facts remain in store | Authorized read + events/incidents → dashboard snapshot/timeline JSON | Complete
B08 | Backend | Operations/data | backend/ghar_sajag/operations.py, store.py | hub_health(); diagnostics(); record_support_action() | audit trail plus counts and independent hub lease | Events/actions/current time → health, diagnostics and auditable support record | Complete
A01 | Caregiver app | App onboarding | app/src/features/onboarding/index.mjs | validateHouseholdDraft(); buildCreateHomeCommand(); installationGate() | Pure draft/result values; no hidden authoritative state | Household draft and install evidence → validation errors, API command, pilot eligibility | Complete
A02 | Caregiver app | App home | app/src/features/home/index.mjs, app/public/* | formatFreshness(); buildHomeView(); timelineLabel() | Rendered projection only; optional A05 cache | Backend snapshot/timeline + phone now → evidence/connectivity cards | Complete
A03 | Caregiver app | App routines | app/src/features/routines/index.mjs | validateMorningRoutine(); buildDesiredConfig(); configStatus() | Desired draft and server/applied versions | Schedule/mode form → schema-aligned desired configuration and status | Complete
A04 | Caregiver app | App incidents | app/src/features/incidents/index.mjs | incidentActions(); actionCommand(); deliveryLabel() | Server incident snapshot and pending client command only | Incident/actor/time → permitted actions and idempotent REST command | Complete
A05 | Caregiver app | App platform | app/src/platform/index.mjs, app/public/service-worker.mjs | ApiClient.request(); VersionedCache.put/get(); pushCapability(); classifyFetchFailure() | Versioned local cache; browser subscription state | Injected fetch/token + command → JSON result/error; cached snapshot → explicit stale flag | Complete
S01 | Shared | Shared contracts | contracts/node.schema.json, cloud.schema.json, config.schema.json, openapi.yaml; scripts/verify_contracts.py | Schema v1 fields and OpenAPI operation IDs | Versioned source files only | Producer payload → structural acceptance or explicit schema/version rejection | Complete
S02 | Shared | Deterministic rules core | shared/include/gs/rules.hpp, shared/src/rules.cpp, domain.hpp | RulesCore::event_overlaps_window/apply_event/evaluate_deadline | Caller-owned RoutineState; no global state or I/O | RoutineConfig + ordered DomainEvent/deadline → deterministic state and IncidentDecision | Complete
S03 | Shared | Firmware security/update | firmware/common/security/security.hpp, security.cpp | CredentialRegistry::install/revoke/get; UpdatePolicy::validate | versioned credential references; no raw secret bytes; running version supplied | Credential/update manifest + verifier → install/reject decision with reason | Complete
T01 | Test / Ops | Simulation/CI | Makefile, tests/cpp/test_main.cpp, tests/python/test_backend.py, tests/js/app.test.mjs, tests/scenarios.json, host/simulator/main.cpp | make verify | Deterministic fixtures and executable assertions | Source tree → contract/build/test/simulator result | Complete
T02 | Test / Ops | Hardware-in-loop tools | tools/hil/provision.py, runner.py, power_profile.py, installation_checklist.md | build_plan(); InstallationRun.observe/result(); summarize() | Provisioning plan, required/pass/fail check set and current capture statistics | Kit IDs / physical observations / current CSV → redacted plan, eligibility, power summary | Complete
T03 | Test / Ops | Deployment/operations | ops/compose.yaml, mosquitto.conf, broker_acl.conf, alerts.yaml, runbook.md | Container/broker configuration and operator procedures | PostgreSQL volume, broker persistence, alert/routing state outside application domain | Deployment secrets/certs/images → regional pilot services and independent alerts | Complete

## LLD Behavior
Low-Level Design — Behavior, Failure and Exit
Code flow, failure semantics, test evidence, target exit criterion and enhancement boundary for every module.
ID | Layer | Module | Code flow | Failure behavior | Host test evidence | Target exit criterion | Further enhancement | LLD status
N01 | Node firmware | Node sensing | Initialize without emitting; record raw edge; require stability for debounce interval; enforce retrigger interval; emit only a qualified transition. | Bounce and repeated PIR holds are suppressed. Initial level is state, not an invented event. Queueing and persistence happen outside this module. | tests/cpp/test_main.cpp: initial, bounce and stable-rise checks | Host behavior passes; hardware exit requires voltage, warm-up, hold-time, wake-loop and placement tests. | Per-board sensor adapters, supervised wiring and measured false-trigger diagnostics. | Complete
N02 | Node firmware | Node radio | Queue once; expose due item; schedule deterministic jittered retry; reject volatile ACK for business events; retire only DURABLE or policy-discard ACK. | Full queue returns false. Radio success is not durable success. Backoff is bounded by the scheduled wake policy. | C++ tests cover immediate send, volatile ACK retention and durable retirement | Host retry/ACK semantics pass; ESP-NOW encryption, channel search, callback timing and loss tests remain. | ESP-NOW adapter first; BLE/Thread transport may implement the same port later. | Complete
N03 | Node firmware | Node power | Never convert an uncalibrated voltage to percentage; classify voltage band; shorten wake for retry; lengthen it at critical voltage; enable only configured wake sources. | Unknown calibration stays UNKNOWN. Software thresholds do not replace cell protection or charger qualification. | C++ tests verify low/unknown bands and retry wake plan | Logic passes; ADC calibration, divider leakage, charge status and full current profile require hardware. | Fuel-gauge adapter, ageing model and observed runtime forecast. | Complete
N04 | Node firmware | Node lifecycle | Validate identity, location, enabled capability and heartbeat range; reject same/older version; replace active snapshot atomically. | No open radio enrollment. Invalid config leaves prior version intact. Service access expires by monotonic deadline. | C++ tests cover invalid capability, valid apply, rollback and 120-second window | Host state transition passes; NVS atomicity, USB jig and authenticated boot registration remain. | Signed delta configuration and controlled node firmware orchestration. | Complete
N05 | Node firmware | Node storage | Ignore periodic heartbeat for flash journal; deduplicate; append before transmit; retire on DURABLE or DISCARDED_POLICY; signal capacity loss. | Full store does not silently drop; gap_marker_required becomes true. Volatile ACK cannot delete business evidence. | C++ tests cover persist-before-send and ACK class behavior; NodeRuntime composition tested | Host semantics pass; CRC/commit-marker flash ring and interrupted-write recovery require board partitions. | Wear-aware compaction and measured retention sizing. | Complete
H01 | Hub firmware | Hub ingest | Authenticate source/session and sequence; copy into bounded queue; return immediately; state task later pops and processes. | Unknown session or full queue rejects and increments observable count. Callback never writes flash or runs rules. | C++ tests cover known/unknown peer and callback-to-worker copy | Host admission passes; frame authentication, payload bounds and ISR/callback latency remain on ESP-IDF. | Per-peer rate caps and captured RF diagnostics. | Complete
H02 | Hub firmware | Hub persistence | Check event key; commit once; expose unacknowledged records; retain until backend application-commit ACK. | Full returns Full and therefore no DURABLE node ACK. Duplicate returns committed equivalence. MQTT PUBACK is intentionally absent from retirement API. | C++ tests cover store, duplicate, pending outbox and application ACK | Host invariants pass; append-only flash record, CRC, checkpoint, wear and 100-cycle crash test remain. | Priority partitions and compaction tuned to measured event volume. | Complete
H03 | Hub firmware | Hub time | Advance from monotonic elapsed time; expand uncertainty by conservative drift; expire anchor after 72 hours; gate absence evaluation by trust and uncertainty. | No anchor, monotonic rollback or expired anchor produces untrusted/expired state. Manual buttons remain valid elsewhere. | C++ tests verify unanchored suppression and trusted bounded estimate | Host math passes; authenticated exchange, reboot lower-bound and optional RTC behavior remain. | Board-measured oscillator drift and generated DST boundary fixtures. | Complete
H04 | Hub firmware | Hub coverage | Require only configured routine sources; refresh contact; report unknown for unseen/expired source; report fault separately from activity. | Current recovery never erases the historical gap. A heartbeat cannot clear an explicit sensor fault. | C++ tests cover never-seen, fresh and 190-second expired lease | Current-state host logic passes; interval reconstruction and physical sensor-path drills remain. | Coverage intervals, mounting-drift checks and source-specific eligibility. | Complete
H05 | Hub firmware | Hub rules adapter | Reset on stable window ID; apply pure S02 reducer; at grace deadline require trusted time, HOME mode and Covered state; create once if no evidence. | Unknown coverage, privacy/away/pause, test data or untrusted time suppresses missing-activity creation with a reason. | C++ tests cover evidence, missing, duplicate deadline, coverage unknown and privacy | Rule paths pass; full scenario replay and long-running device timer/reboot tests remain. | Additional deterministic routines without opaque risk scores. | Complete
H06 | Hub firmware | Hub resident interface | Map physically distinct controls to explicit event kinds; state whether action was saved locally or accepted remotely; use fixed prompt flag only. | No microphone or generated speech. Offline Call family remains stored and explicitly says internet unavailable. | C++ tests verify Call family event and offline wording | Host event/feedback contract passes; buttons, latching switch, OLED/LED, audio load and resident usability remain. | Localized fixed prompts and accessibility options after testing. | Complete
H07 | Hub firmware | Hub lifecycle/config | Validate home/timezone and ordered window boundaries; reject same/older version; replace atomically; expose applied version. | Invalid version never partially mutates active rules. Device update orchestration is separated by S03 policy. | C++ tests cover valid apply and stale-version rejection | Host atomic snapshot passes; NVS transaction, reboot restore, provisioning and OTA binding remain. | Staged rollout, rollback health window and fleet cohort controls. | Complete
H08 | Hub firmware | Hub cloud link | Send only when connected/due; prioritize Call family over history; use bounded reconnect schedule; retire on backend commit ACK. | Disconnect/backoff preserves outbox. Transport ACK cannot call application_commit_ack. Original event time is unchanged. | C++ tests cover urgent ordering and application-level retirement; simulator replays one offline record | Host scheduling passes; Wi-Fi/TLS/MQTT, ACL, broker failure and 72-hour field replay remain. | Cellular adapter only after cost and operational design. | Complete
B01 | Backend | Identity/access | Resolve exact home-scoped membership; distinguish manage/read role sets; enforce expiry; audit grant/revoke. | No global caregiver access and no serial-number authorization. Cross-home lookup fails closed. | test_B01_F01_membership_is_tenant_scoped | Domain policy passes; production OIDC verification, token audience/issuer and database row-level controls remain. | Delegated care teams and support impersonation with explicit approval/audit. | Complete
B02 | Backend | Home/consent | Require valid timezone/name and active resident consent; create owner membership; require distinct primary/backup; privacy on withdrawal. | Duplicate home, missing consent or same backup fails. Purchase does not imply consent and PIR never identifies a resident. | F01 role test and test_B02_consent_withdrawal_enters_privacy | Domain state passes; invitation tokens, durable repository and deletion workflow remain. | Multiple residents without passive identity inference. | Complete
B03 | Backend | Event ingestion | Verify known home, event kind and timing fields; use unique event key; append audit in the same host operation. | Unknown home/kind and invalid timing fail. Duplicate returns prior commit without another domain effect. | test_B03_ingest_is_idempotent | Domain idempotency passes; PostgreSQL transaction/outbox, MQTT consumer and commit ACK adapter remain. | Partitioning and batch replay after measured load. | Complete
B04 | Backend | Incident workflow | Create once by stable key; claim with bounded lease; prevent live dual ownership; acknowledge then explicitly resolve; audit human action. | Closed incidents reject claim; another live owner causes conflict; home mismatch behaves as not found. | call idempotency and test_B04_claim_lease_prevents_double_ownership | State machine passes; database compare-and-set, HANDOFF_TO_BACKUP and concurrency load tests remain. | Structured Contacted/Unable-to-reach outcome and professional adapter only under contract. | Complete
B05 | Backend | Notification routing | Schedule primary now and backup at +300 s; select due open jobs; keep provider acceptance separate from human ACK; cancel pending jobs after ACK; summarize coverage honestly. | No recipient means no invented route; tests never create production notice; a summary cannot resolve an incident; duplicate keys reuse prior intent. | B04/B05 route tests, F09 notice test, F14 summary test and TEST exclusion | Domain routing passes; real Web Push, worker lease, retry/jitter and phone delivery tests remain. | Funded SMS/voice and emergency-response service only with explicit provider contract. | Complete
B06 | Backend | Fleet/config | Authorize owner; prevent cross-home device rebind; increment desired version; record only known applied versions; audit. | Unknown future apply and device conflict reject. Desired does not equal applied until hub reports it. | test_B06_config_version_and_device_binding | Version semantics pass; PostgreSQL, one-use claim, signed manifest publication and cohort rollout remain. | Fleet cohorts, staged update and field diagnostics. | Complete
B07 | Backend | Read models/API | Sort by original occurrence; compute hub lease from server receipts; choose latest activity independently; expose incidents and fetched time. | Fresh phone fetch cannot make stale hub data current. Test events are excluded from production timeline. | test_B07_B08_snapshot_separates_activity_from_reachability | Projection logic passes; pagination, SSE, OpenAPI conformance and React integration remain. | Materialized PostgreSQL projections and regional read replicas only when needed. | Complete
B08 | Backend | Operations/data | Evaluate hub server-receipt lease; count each domain independently; record support actions without editing historical events. | Broker retained online state is not authoritative. In-memory store is a host adapter, not a durable production claim. | B07/B08 snapshot test and diagnostics assertions | Host observability passes; PostgreSQL retention/export, independent uptime and restore drill remain. | Privacy-preserving fleet metrics and support bundle redaction. | Complete
A01 | Caregiver app | App onboarding | Require home/timezone/resident consent/distinct caregiver pair; construct idempotent home command; require every enabled input plus hub controls and real delivery drill. | Missing check remains visible and blocks unattended eligibility. No default consent or inferred backup. | Node tests: onboarding validation and installation gate | Domain/UI model passes; React form, QR claim, accessibility and real phone workflow remain. | Installer role UX and multilingual consent evidence. | Complete
A02 | Caregiver app | App home | Format separate freshness; show household activity only; render hub availability independently; explicitly state no activity evidence is not presence proof. | Stale/never-seen is visible. No safe/fine/wellbeing label and no resident identity inference. | Home-view separation test; static responsive prototype included | View-model tests pass; React/PWA accessibility, localization and supported-phone tests remain. | Weekly digest and richer source explanations. | Complete
A03 | Caregiver app | App routines | Validate minute ranges/grace; deduplicate locations; build versioned config; compare desired against applied without pretending pending succeeded. | Invalid mode/routine throws explicit client error. Newer hub version becomes conflict, not silent overwrite. | Routine command and desired/applied status test | Pure UI logic passes; screen, timezone boundary preview and backend persistence remain. | Multiple deterministic routine templates. | Complete
A04 | Caregiver app | App incidents | Hide mutation actions when another live owner holds lease; distinguish claim, acknowledge and resolve; label provider acceptance separately. | Offline action cannot become authoritative. Unsupported action is rejected before request. | Incident ownership/action and command-path test | View/action rules pass; optimistic-pending UI, SSE reconciliation and caregiver comprehension remain. | Contact outcome and deliberate handoff UI. | Complete
A05 | Caregiver app | App platform | Attach bearer/idempotency headers; classify auth/service/network failures; retain only newer cache versions; expose exact push capability reason. | Cache never claims server commit. Push permission/subscription is not human acknowledgement. | Cache and push capability test | Framework-neutral adapter passes; OIDC SDK, service worker push handler, IndexedDB and real browser tests remain. | Native wrapper only if PWA constraints justify it. | Complete
S01 | Shared | Shared contracts | Keep node event identity, cloud timestamps/test flag and desired configuration version canonical; validate source structure in CI. | Unknown additional fields fail in JSON schemas; schema change requires a new version and compatibility tests. | make contracts verifies three required-field sets and API surface | Source contracts pass; CBOR CDDL/generated C++/Python/TypeScript bindings and golden vectors remain. | Generated clients and formal compatibility matrix. | Complete
S02 | Shared | Deterministic rules core | Use uncertainty interval overlap; ignore tests; gate modes; record evidence IDs; produce stable incident key only after all eligibility gates. | Time, coverage and mode uncertainty return a reason instead of a false incident. Same state/input is replayable. | C++ rule tests and HubRuntime composition | Host reducer passes; scenario-property, reorder and reboot checkpoint tests remain. | Additional transparent rules compiled into the same host/firmware core. | Complete
S03 | Shared | Firmware security/update | Reject missing/stale credential; match board; prevent rollback; validate hash text; delegate signature verification to injected production crypto. | Host verifier is a seam, not cryptographic proof. Wrong board/version/hash/signature fails closed. | C++ tests cover install, rollback, revoke and manifest policy | Policy passes; protected NVS/secure element, real SHA-256/ECDSA, secure boot and rollback recovery remain. | Key rotation and manufacturing HSM workflow. | Complete
T01 | Test / Ops | Simulation/CI | Validate contracts; compile strict C++17; execute 52 checks; run simulator; run 10 Python and 6 Node tests. | Any command returns non-zero. Report never claims RF/power/provider coverage. | VERIFICATION_REPORT.md records the successful 7 September 2026 run | Current host suite green; add CI runner, fuzz/property tests and coverage thresholds. | Nightly long replay and hardware-in-loop lane. | Complete
T02 | Test / Ops | Hardware-in-loop tools | Require four unique nodes; never print claim token; fail unknown checks; gate eligibility on every required check; summarize measured current. | Scripts cannot prove a board action without an adapter/evidence. Sensitive plan is explicitly separated from console output. | Syntax/import covered by backend run context; physical execution deliberately pending | Host tooling exists; serial adapter, fault injector, power instrument and installed-home run are required. | Automated relay/power-cycle jig and signed evidence bundle. | Complete
T03 | Test / Ops | Deployment/operations | Use TLS client identity and topic ACL; durable broker/database; alert ingest/backlog/fleet/backup; follow idempotent recovery runbook. | Example files omit secrets by design and are not a production deployment certificate. Restore and provider failures remain explicit. | Configuration reviewed structurally; live broker/database/backup drill pending | Examples complete; staging deployment, secret store, migrations, external monitoring and restore evidence remain. | Horizontal process replicas before service decomposition. | Complete

## Communication
Communication and Persistence Matrix
Logical contracts are implemented on the host. Rows marked Pending still need their real ESP32, network, provider or phone binding.
Flow | Producer | Consumer | Mode | Contract | Reliability / acknowledgement | Security / privacy | Offline behavior | Host status | Target status | Target exit evidence
C01 | PIR/reed/button node | Hub H01 | ESP-NOW planned | S01 node event v1 | Retain before send; retry; retire only after DURABLE/policy-discard ACK | Authorized peer/session; payload validation; no identity inference | Node retains bounded events until hub is available | Complete | Pending | Loss/duplicate/reboot RF test with one physical event appearing once
C02 | Radio callback | Hub state_core | Bounded FreeRTOS queue | Fixed-value admitted event | Callback copies and returns; queue-full rejection is observable | No flash or rule execution inside callback | Local queue/journal remain independent of WAN | Complete | Pending | Measured callback latency, queue saturation and watchdog test
C03 | Hub state_core | Hub flash journal | Local append-only storage | H02 record + commit marker | Commit precedes DURABLE node ACK; duplicate key is idempotent | No sensitive raw media; bounded evidence only | Persists through WAN outage and reboot | Complete | Pending | CRC/commit, interrupted-write, wear and 100-cycle reset evidence
C04 | Hub H08 | Backend B03 | Wi-Fi + MQTT/TLS planned | S01 cloud event v1 | MQTT transport ACK is not business commit; backend application ACK retires | Client identity, TLS and topic ACL | Hub outbox keeps original occurrence time and replays | Complete | Pending | Staging broker loss/reconnect plus 72-hour replay without duplicate effects
C05 | Backend API | Caregiver app | HTTPS/JSON | OpenAPI v1 | Idempotency key on commands; server is authoritative | OIDC bearer; home-scoped authorization | Versioned cache is visibly stale, never authoritative | Complete | Pending | Real OIDC/API test on supported phones including stale/offline state
C06 | Backend B05 | Caregiver phone | Web Push planned | Notification job + delivery state | Provider acceptance, phone receipt and human ACK remain separate | Consent/route scoped; no health assurance claim | Backup route is bounded; provider failure remains visible | Complete | Pending | Primary/backup real-phone TEST drill including provider failure
C07 | App/backend B06 | Hub H07 / node N04 | HTTPS then MQTT/TLS planned | Versioned HomeConfig/NodeConfig | Same/older version rejected; apply reported separately | Authorized owner; signed manifest for firmware path | Existing valid config stays active | Complete | Pending | Atomic apply, reboot restore, stale/conflict and rollback tests
C08 | Resident controls | Hub H06/state_core | GPIO/I2C/local feedback | OK/Call/Privacy domain events | Local persistence status shown immediately; remote acceptance later | Physical privacy action; fixed prompts only | OK/Call can save locally when WAN is down | Complete | Pending | Button/switch/display/buzzer test with caregiver comprehension evidence
C09 | Update service | Hub/node bootloader | HTTPS/TLS OTA planned | S03 signed update manifest | Rollback prevented; recovery slot required | Real hash/signature, protected key and secure boot | Prior image remains recoverable | Partial | Pending | Signed OTA, wrong-board, corrupt-image, rollback and recovery drill

## Workplan
Ordered P0 Completion Workplan
The next work starts with target compilation and one physical vertical slice—not with additional features.
Order | Step | Work item | Primary owner | Depends on | Deliverable | Exit evidence | Status | Priority
1 | 1 | Run and trace host baseline | Software | Existing repository | Repeatable make verify run and event trace | Contracts + 52 C++ + simulator + 10 Python + 6 Node tests pass | Complete | P0
2 | 2 | Pin ESP-IDF/toolchain | Firmware | Board identity | Version lock and reproducible build environment | Clean build records exact framework/toolchain versions | Not Started | P0
3 | 2 | Create ESP32-C3 node target/profile | Firmware | Pinned toolchain | Node target, partitions and boot diagnostics | Board compiles, flashes and reports version/reset reason | Not Started | P0
4 | 2 | Create DevKit V1 hub target/profile | Firmware | Pinned toolchain | Hub target, partitions and boot diagnostics | Board compiles, flashes and reports version/reset reason | Not Started | P0
5 | 2 | Freeze GPIO/voltage/power constraints | HW + Firmware | Purchased parts | Reviewed pin/power table | No boot-strap conflict; measured voltage/current boundaries recorded | Not Started | P0
6 | 3 | Bind AM312 PIR and qualification logic | Firmware | C3 target | GPIO adapter using N01 | Warm-up, hold, bounce and retrigger behavior measured | Not Started | P0
7 | 3 | Bind retained node storage | Firmware | C3 partitions | N05 flash/NVS implementation | Interrupted write/reboot does not silently lose acknowledged state | Not Started | P0
8 | 3 | Bind ESP-NOW node ↔ hub transport | Firmware | Both board targets | N02/H01 adapters and application ACK | Loss, duplicate, reboot and retry cases pass | Not Started | P0
9 | 3 | Bind durable hub journal | Firmware | Hub target | H02 flash journal | One motion event persists once with original event time | Not Started | P0
10 | 3 | Expose local evidence dashboard | Firmware/App | Hub journal | Minimal local/API view | Physical motion appears once; unknown coverage never becomes safety claim | Not Started | P0
11 | 4 | Bind trusted time + coverage gates | Firmware | Vertical slice | H03/H04 target adapters | Reboot/drift/lease-expiry cases suppress false missing activity | Not Started | P0
12 | 4 | Bind routine decision path | Firmware | Trusted time/coverage | H05 on target | Normal, missing, privacy, away/pause cases pass | Not Started | P0
13 | 4 | Bind I'm OK, Call family and privacy controls | HW + Firmware | Hub target | H06 GPIO/display/buzzer integration | Offline/online feedback and durable action tests pass | Not Started | P0
14 | 5 | Implement PostgreSQL repositories, migrations and RLS | Backend | Stable contracts | Durable tenant-scoped store | Idempotency, concurrency, retention and restore tests pass | Not Started | P0
15 | 5 | Integrate OIDC + MQTT/TLS | Backend/Firmware | Staging services | Authenticated API and broker path | Cross-home access fails; reconnect/replay succeeds | Not Started | P0
16 | 5 | Integrate Web Push + worker leases | Backend/App | OIDC/API | Primary/backup notification pipeline | Real phones pass TEST, failure and duplicate cases | Not Started | P0
17 | 5 | Production PWA integration | App | Real API/providers | Accessible caregiver application | Supported phones pass freshness, offline and incident workflows | Not Started | P0
18 | 5 | Implement real crypto and signed OTA | Security/Firmware | Board boot path | Secure update/recovery path | Signature, rollback, corrupt-image and recovery tests pass | Not Started | P0
19 | 6 | Install and tune four sources | System test | Integrated kit | Four-node home installation | RF, sensor, power and placement evidence recorded | Not Started | P0
20 | 6 | Run outage, reset, storage and restore drills | System test/Ops | Installed kit + staging | Repeatable resilience report | 72-hour WAN outage/replay and recovery gates pass | Not Started | P0
21 | 6 | Resident/caregiver comprehension and consent gate | Product/Test | Complete workflows | Dated pilot-readiness evidence | Users distinguish activity, offline, provider and human-action states | Not Started | P0

## Verification
Verification Evidence and Open Gates
Latest host suite re-run: 8 September 2026. Pending rows are intentionally not represented by the green host result.
Check ID | Verification scope | Layer | Result | Evidence | What is not covered | Command / source | Evidence date
V01 | Contract structure | S01 | Passed | 3 JSON schemas plus OpenAPI surface verified | Generated bindings and wire compatibility vectors | make contracts / scripts/verify_contracts.py | 2026-09-08
V02 | Strict portable C++17 build | N/H/S | Passed | g++ with -Wall -Wextra -Werror -pedantic | ESP-IDF target compilation | make cpp-tests | 2026-09-08
V03 | Portable C++ behavior | N/H/S | Passed | 52 assertions passed | GPIO, RF, flash, reset and power behavior | build/cpp_tests | 2026-09-08
V04 | Host end-to-end simulator | N/H | Passed | Activity persisted; false missing suppressed; one offline record replayed once | Real devices, broker and long outage | make simulator | 2026-09-08
V05 | Backend domain | B | Passed | 10 unittest cases passed | PostgreSQL, OIDC, MQTT, Web Push and concurrency | python -m unittest | 2026-09-08
V06 | Caregiver app domain | A | Passed | 6 Node.js tests passed | Production UI, accessibility, service worker and phones | node --test tests/js/*.test.mjs | 2026-09-08
V07 | ESP32 board build/flash | N/H | Pending | No target build evidence yet | ESP-IDF, partitions, boot diagnostics | Workplan step 2
V08 | GPIO/sensor and ESP-NOW vertical slice | N/H | Pending | No physical event evidence yet | PIR/reed/button, RF loss/duplicates and durable ACK | Workplan step 3
V09 | Flash/power/reset/HIL | N/H/T02 | Pending | Scaffolding only | Current profile, interrupted writes, resets and battery behavior | tools/hil/*
V10 | Production services | B/A/H | Pending | Host adapters only | PostgreSQL, OIDC, MQTT/TLS, Web Push and real phones | Workplan step 5
V11 | Production crypto and OTA recovery | S03/N/H | Pending | Fail-closed policy seam only | Real signature/hash, protected keys, secure boot and recovery | Workplan step 5
V12 | Four-node installed-home gate | All | Pending | No field run evidence yet | RF, power, false/missed events, 72-hour WAN outage and user comprehension | Workplan step 6