## Dashboard
Ghar Sajag Validation Dashboard — v1.5.4
Metric | Current evidence |  | Functional category | Cases
Functional scenarios passed | 68 / 68 |  | Expected | 9
Dummy streams passed | 5 / 5 |  | Morning | 10
HTTP integration tests | 16 / 16 PASS |  | Door | 11
Python tests | 24 / 24 PASS |  | Inactivity | 10
JavaScript tests | 10 / 10 PASS |  | Transport | 5
C++ checks per profile | 80 PASS |  | Caregiver | 2
P0 requirement mappings | 24 / 24 |  | Configuration | 1
Browser automation | MANUAL_REQUIRED |  | Negative | 9
Physical hardware acceptance | PENDING |  | Diagnostics | 11
Release interpretation
HOST/SOFTWARE | PASS | All mandatory host/software layers passed.
BROWSER/PWA | MANUAL_REQUIRED | Playwright not installed in current evidence environment; use generated manual plan or make release-gate-browser.
PHYSICAL/HIL | PENDING | Real sensors, RF, power, flash, OTA, notification provider and installed-home coverage remain separate gates.
RULE | Do not release on mandatory FAIL | A host PASS is not a safety certification or physical product acceptance.
Key commands
make validation-fast | Developer regression
make release-gate | Full host/software release gate
make release-gate-browser | Full gate with browser automation mandatory
make manual-test-plan | Regenerate manual checklist from canonical catalog

## Master Test Register
Test ID | Layer | Category | Test / Scenario | Requirements | Input / Preconditions | Steps / Command | Expected Result | Automation | Current Status | Manual Result | Evidence / Source | Defect ID | Owner | Notes
FNC-001 | Connected Functional | expected | Room 1 motion is preserved as exact positive activity | F05, F11 | Reset synthetic state before case | Inject MOTION from room1 | home.latest_activity.kind = MOTION home.latest_activity.location = room1 home.latest_activity.tone = positive | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-002 | Connected Functional | expected | Kitchen motion is preserved as exact positive activity | F05, F11 | Reset synthetic state before case | Inject MOTION from kitchen | home.latest_activity.location = kitchen home.latest_activity.tone = positive | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-003 | Connected Functional | expected | Pooja motion is preserved as exact positive activity | F05, F11 | Reset synthetic state before case | Inject MOTION from pooja | home.latest_activity.location = pooja home.latest_activity.tone = positive | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-004 | Connected Functional | expected | Normal daytime door opening is green and explicit | F09, F11 | Reset synthetic state before case | Inject DOOR_OPEN from entry | home.latest_activity.kind = DOOR_OPEN home.latest_activity.tone = positive home.latest_activity.details.unexpected = False | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-005 | Connected Functional | expected | Door open and close remain chronological and explicit | F09, F11 | Reset synthetic state before case | Inject DOOR_OPEN from entry Advance simulated clock by 60 seconds Inject DOOR_CLOSED from entry | home.recent_events starts with ['DOOR_CLOSED', 'DOOR_OPEN'] by kind home.door_status.state = CLOSED | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-006 | Connected Functional | expected | I am OK remains a distinct green self-check-in | F06, F11 | Reset synthetic state before case | Inject OK_PRESSED from room1 | home.latest_activity.kind = OK_PRESSED home.latest_activity.tone = positive | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-007 | Connected Functional | expected | Call Family opens exactly one incident and two routes | F07, F13 | Reset synthetic state before case | Inject CALL_FAMILY from room1 | incidents where {"kind": "CALL_FAMILY", "state": "OPEN"} count = 1 notifications where {} count = 2 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-008 | Connected Functional | expected | I am OK after Call Family is newer but does not resolve the request | F06, F07, F11 | Reset synthetic state before case | Inject CALL_FAMILY from room1 Advance simulated clock by 60 seconds Inject OK_PRESSED from room1 | home.recent_events starts with ['OK_PRESSED', 'CALL_FAMILY'] by kind incidents where {"kind": "CALL_FAMILY", "state": "OPEN"} count = 1 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-009 | Connected Functional | expected | Later activities remain visible after missing-morning alert | F08, F11 | Reset synthetic state before case | Advance simulated clock by 1300 seconds Inject MOTION from room1 Advance simulated clock by 60 seconds Inject MOTION from kitchen Inject DOOR_OPEN from entry | incidents where {"kind": "MISSING_MORNING_ACTIVITY"} count = 1 home.recent_events where {"kind": "MOTION"} count >= 2 home.recent_events where {"kind": "DOOR_OPEN"} count = 1 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-010 | Connected Functional | morning | Covered morning with no evidence creates one concern | F08 | Reset synthetic state before case | Advance simulated clock by 1300 seconds | simulation.reason = no_qualifying_evidence incidents where {"kind": "MISSING_MORNING_ACTIVITY"} count = 1 notifications where {} count = 2 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-011 | Connected Functional | morning | Kitchen motion satisfies morning routine | F05, F08 | Reset synthetic state before case | Inject MOTION from kitchen Advance simulated clock by 1300 seconds | simulation.reason = evidence_present incidents where {"kind": "MISSING_MORNING_ACTIVITY"} count = 0 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-012 | Connected Functional | morning | Pooja motion satisfies morning routine | F05, F08 | Reset synthetic state before case | Inject MOTION from pooja Advance simulated clock by 1300 seconds | simulation.reason = evidence_present incidents where {"kind": "MISSING_MORNING_ACTIVITY"} count = 0 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-013 | Connected Functional | morning | Room 1 motion does not silently satisfy kitchen/pooja morning policy | F04, F08 | Reset synthetic state before case | Inject MOTION from room1 Advance simulated clock by 1300 seconds | incidents where {"kind": "MISSING_MORNING_ACTIVITY"} count = 1 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-014 | Connected Functional | morning | Main-door activity does not silently satisfy kitchen/pooja morning policy | F04, F08 | Reset synthetic state before case | Inject DOOR_OPEN from entry Advance simulated clock by 1300 seconds | incidents where {"kind": "MISSING_MORNING_ACTIVITY"} count = 1 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-015 | Connected Functional | morning | Explicit I am OK satisfies morning check-in independently of PIR | F06, F08 | Reset synthetic state before case | Inject OK_PRESSED from room1 Advance simulated clock by 1300 seconds | simulation.explicit_ok is true/non-empty incidents where {"kind": "MISSING_MORNING_ACTIVITY"} count = 0 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-016 | Connected Functional | morning | Missing sensor coverage suppresses inactivity interpretation | E01, F08 | Reset synthetic state before case | {"action": "node", "enabled": false, "node": "kitchen"} Advance simulated clock by 1300 seconds | simulation.reason = coverage_unknown incidents where {"kind": "MISSING_MORNING_ACTIVITY"} count = 0 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-017 | Connected Functional | morning | Untrusted clock suppresses time-based morning concern | E06, F08 | Reset synthetic state before case | Set trusted clock disabled Advance simulated clock by 1300 seconds | simulation.reason = time_untrusted incidents where {"kind": "MISSING_MORNING_ACTIVITY"} count = 0 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-018 | Connected Functional | morning | Morning concern detected offline replays with original detection time | E03, F08 | Reset synthetic state before case | Set WAN disabled Advance simulated clock by 1300 seconds Advance simulated clock by 60 seconds Set WAN enabled | incidents where {"kind": "MISSING_MORNING_ACTIVITY"} count = 1 timeline where {"kind": "MISSING_MORNING_ACTIVITY", "occurred_at": 2300} count = 1 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-019 | Connected Functional | morning | Repeated deadline evaluation does not create duplicate missing incident | E02, F08 | Reset synthetic state before case | Advance simulated clock by 1300 seconds {"action": "deadline"} {"action": "deadline"} | incidents where {"kind": "MISSING_MORNING_ACTIVITY"} count = 1 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-020 | Connected Functional | door | Door opening in configured quiet hours is unexpected/red | F09 | Reset synthetic state before case | Inject DOOR_OPEN from entry (late-night) | home.latest_activity.details.unexpected = True home.latest_activity.tone = danger | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-021 | Connected Functional | door | Quiet-hour door opening is normal when the household disables that rule | F09, E07 | Reset synthetic state before case | Change household settings: {"quiet_hours_enabled": false} Inject DOOR_OPEN from entry (late-night) | home.latest_activity.details.unexpected = False home.latest_activity.tone = positive | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-022 | Connected Functional | door | Late-night door concern is suppressed in AWAY mode | F09, F10 | Reset synthetic state before case | Set home mode to AWAY Inject DOOR_OPEN from entry (late-night) | home.latest_activity.details.unexpected = False home.mode = AWAY | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-023 | Connected Functional | door | Late-night door concern is suppressed in PAUSED mode | F09, F10 | Reset synthetic state before case | Set home mode to PAUSED Inject DOOR_OPEN from entry (late-night) | home.latest_activity.details.unexpected = False home.mode = PAUSED | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-024 | Connected Functional | door | Late-night door concern is suppressed in VISITOR mode | F09, F10 | Reset synthetic state before case | Set home mode to VISITOR Inject DOOR_OPEN from entry (late-night) | home.latest_activity.details.unexpected = False home.mode = VISITOR | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-025 | Connected Functional | door | Door left open before threshold does not warn | F09 | Reset synthetic state before case | Inject DOOR_OPEN from entry Advance simulated clock by 299 seconds | timeline where {"kind": "DOOR_LEFT_OPEN"} count = 0 home.door_status.left_open = False | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-026 | Connected Functional | door | Door left open at threshold creates one red warning | F09 | Reset synthetic state before case | Inject DOOR_OPEN from entry Advance simulated clock by 300 seconds | timeline where {"kind": "DOOR_LEFT_OPEN", "tone": "danger"} count = 1 home.door_status.left_open = True | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-027 | Connected Functional | door | Door closed before threshold remains normal | F09 | Reset synthetic state before case | Inject DOOR_OPEN from entry Advance simulated clock by 240 seconds Inject DOOR_CLOSED from entry | timeline where {"kind": "DOOR_LEFT_OPEN"} count = 0 home.latest_activity.kind = DOOR_CLOSED home.latest_activity.tone = positive | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-028 | Connected Functional | door | Closing a left-open door clears current condition and preserves duration | F09 | Reset synthetic state before case | Inject DOOR_OPEN from entry Advance simulated clock by 360 seconds Inject DOOR_CLOSED from entry | timeline where {"kind": "DOOR_LEFT_OPEN"} count = 1 home.latest_activity.details.resolved_left_open = True {"ge": 360, "path": "home.latest_activity.details.open_duration_s"} home.door_status.state = CLOSED | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-029 | Connected Functional | door | Standalone close state does not invent a left-open warning | F09 | Reset synthetic state before case | Inject DOOR_CLOSED from entry | timeline where {"kind": "DOOR_LEFT_OPEN"} count = 0 home.door_status.state = CLOSED | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-030 | Connected Functional | door | Door-left-open threshold follows household configuration | F09, E07 | Reset synthetic state before case | Change household settings: {"door_open_timeout_seconds": 120} Inject DOOR_OPEN from entry Advance simulated clock by 119 seconds Advance simulated clock by 1 seconds | timeline where {"kind": "DOOR_LEFT_OPEN"} count = 1 home.door_status.left_open = True | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-031 | Connected Functional | inactivity | No activity before configured threshold does not alert | F11 | Reset synthetic state before case | Change household settings: {"daytime_inactivity_seconds": 300} Set local minute to 600 Advance simulated clock by 299 seconds | timeline where {"kind": "DAYTIME_INACTIVITY"} count = 0 incidents where {"kind": "DAYTIME_INACTIVITY"} count = 0 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-032 | Connected Functional | inactivity | No activity at configured threshold opens check-in workflow | F11, F12 | Reset synthetic state before case | Change household settings: {"daytime_inactivity_seconds": 300} Set local minute to 600 Advance simulated clock by 300 seconds | timeline where {"kind": "DAYTIME_INACTIVITY", "tone": "danger"} count = 1 incidents where {"kind": "DAYTIME_INACTIVITY", "state": "OPEN"} count = 1 notifications where {} count = 2 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-033 | Connected Functional | inactivity | Activity resets daytime inactivity timer | F05 | Reset synthetic state before case | Change household settings: {"daytime_inactivity_seconds": 300} Set local minute to 600 Advance simulated clock by 240 seconds Inject MOTION from room1 Advance simulated clock by 240 seconds | timeline where {"kind": "DAYTIME_INACTIVITY"} count = 0 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-034 | Connected Functional | inactivity | Disabled daytime inactivity policy produces no concern | E07 | Reset synthetic state before case | Change household settings: {"daytime_inactivity_enabled": false, "daytime_inactivity_seconds": 300} Set local minute to 600 Advance simulated clock by 600 seconds | timeline where {"kind": "DAYTIME_INACTIVITY"} count = 0 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-035 | Connected Functional | inactivity | Daytime inactivity is suppressed in AWAY mode | F10 | Reset synthetic state before case | Change household settings: {"daytime_inactivity_seconds": 300} Set local minute to 600 Set home mode to AWAY Advance simulated clock by 300 seconds | timeline where {"kind": "DAYTIME_INACTIVITY"} count = 0 home.mode = AWAY | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-036 | Connected Functional | inactivity | Daytime inactivity is suppressed in PAUSED mode | F10 | Reset synthetic state before case | Change household settings: {"daytime_inactivity_seconds": 300} Set local minute to 600 Set home mode to PAUSED Advance simulated clock by 300 seconds | timeline where {"kind": "DAYTIME_INACTIVITY"} count = 0 home.mode = PAUSED | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-037 | Connected Functional | inactivity | Daytime inactivity is suppressed in VISITOR mode | F10 | Reset synthetic state before case | Change household settings: {"daytime_inactivity_seconds": 300} Set local minute to 600 Set home mode to VISITOR Advance simulated clock by 300 seconds | timeline where {"kind": "DAYTIME_INACTIVITY"} count = 0 home.mode = VISITOR | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-038 | Connected Functional | inactivity | Daytime inactivity is suppressed when observation coverage is unavailable | E01 | Reset synthetic state before case | Change household settings: {"daytime_inactivity_seconds": 300} Set local minute to 600 {"action": "node", "enabled": false, "node": "kitchen"} Advance simulated clock by 300 seconds | timeline where {"kind": "DAYTIME_INACTIVITY"} count = 0 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-039 | Connected Functional | inactivity | Daytime inactivity is suppressed when time is untrusted | E06 | Reset synthetic state before case | Change household settings: {"daytime_inactivity_seconds": 300} Set local minute to 600 Set trusted clock disabled Advance simulated clock by 300 seconds | timeline where {"kind": "DAYTIME_INACTIVITY"} count = 0 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-040 | Connected Functional | inactivity | Daytime inactivity does not fire outside configured daytime window | E06 | Reset synthetic state before case | Change household settings: {"daytime_inactivity_seconds": 300} Set local minute to 1380 Advance simulated clock by 300 seconds | timeline where {"kind": "DAYTIME_INACTIVITY"} count = 0 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-041 | Connected Functional | transport | WAN loss keeps local evidence while backend view is stale | E03, E04 | Reset synthetic state before case | Set WAN disabled Inject MOTION from kitchen Advance simulated clock by 240 seconds | simulation.activity_seen is true/non-empty {"gt": 0, "path": "simulation.pending_cloud"} home.hub_reachable = False timeline where {"kind": "MOTION"} count = 0 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-042 | Connected Functional | transport | WAN reconnect replays pending event exactly once | E02, E03 | Reset synthetic state before case | Set WAN disabled Inject MOTION from kitchen Set WAN enabled | simulation.pending_cloud = 0 timeline where {"kind": "MOTION"} count = 1 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-043 | Connected Functional | transport | Node link recovery replays retained event exactly once | E02 | Reset synthetic state before case | {"action": "node", "enabled": false, "node": "kitchen"} Inject MOTION from kitchen {"action": "node", "enabled": true, "node": "kitchen"} | timeline where {"kind": "MOTION"} count = 1 simulation.nodes.1.retained = 0 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-044 | Connected Functional | transport | Duplicate radio replay is stored once by backend | E02 | Reset synthetic state before case | Inject MOTION from kitchen {"action": "duplicate"} | timeline where {"kind": "MOTION"} count = 1 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-045 | Connected Functional | transport | Call Family survives WAN outage and opens one incident on reconnect | E03, F07 | Reset synthetic state before case | Set WAN disabled Inject CALL_FAMILY from room1 Set WAN enabled | incidents where {"kind": "CALL_FAMILY"} count = 1 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-046 | Connected Functional | caregiver | Notification provider acceptance does not acknowledge incident | F12, F13 | Reset synthetic state before case | Advance simulated clock by 1300 seconds {"action": "notify"} | incidents where {"kind": "MISSING_MORNING_ACTIVITY", "state": "OPEN"} count = 1 notifications where {"state": "PROVIDER_ACCEPTED"} count >= 1 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-047 | Connected Functional | caregiver | Claim acknowledge resolve closes incident and cancels pending routes | F12, F13 | Reset synthetic state before case | Advance simulated clock by 1300 seconds {"as": "iid", "capture": "first_incident"} {"action": "claim", "incident_id": "$iid"} {"action": "acknowledge", "incident_id": "$iid"} {"action": "resolve", "incident_id": "$iid"} | incidents where {"state": "RESOLVED"} count = 1 notifications where {"state": "CANCELLED"} count = 2 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-048 | Connected Functional | configuration | Changing household policy creates a new config version | E07 | Reset synthetic state before case | Change household settings: {"door_open_timeout_seconds": 180} | {"ge": 2, "path": "settings.config_version"} settings.door_open_timeout_seconds = 180 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-049 | Connected Functional | negative | User-facing privacy event is not accepted by simulator controls | F02 | Reset synthetic state before case | Inject PRIVACY_ON from room1 |  | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-050 | Connected Functional | negative | Sensor capability mismatch is rejected | E07 | Reset synthetic state before case | Inject DOOR_OPEN from kitchen |  | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-051 | Connected Functional | negative | Resident button event cannot be injected through door sensor | E07 | Reset synthetic state before case | Inject OK_PRESSED from entry |  | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-052 | Connected Functional | negative | Negative simulated time advance is rejected | NFR-08 | Reset synthetic state before case | Advance simulated clock by -1 seconds |  | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-053 | Connected Functional | negative | Invalid local minute is rejected | E06 | Reset synthetic state before case | Set local minute to 1440 |  | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-054 | Connected Functional | negative | Unsupported mode is rejected | F10 | Reset synthetic state before case | Set home mode to PRIVACY |  | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-055 | Connected Functional | negative | Unsafe door timeout setting is rejected | E07 | Reset synthetic state before case | Change household settings: {"door_open_timeout_seconds": 20} |  | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-056 | Connected Functional | negative | Unsafe inactivity threshold is rejected | E07 | Reset synthetic state before case | Change household settings: {"daytime_inactivity_seconds": 200} |  | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-057 | Connected Functional | negative | Unknown node cannot inject sensor data | E07 | Reset synthetic state before case | Inject MOTION from garage |  | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-058 | Connected Functional | diagnostics | Node fault LOW_BATTERY maps to stable diagnostics | E01, E10 | Reset synthetic state before case | Inject LOW_BATTERY on None Run Troubleshoot on None | devices where {"active": true, "code": "GS-N001", "health": "DEGRADED", "id": "kitchen"} count = 1 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-059 | Connected Functional | diagnostics | Node fault BATTERY_DEPLETED maps to stable diagnostics | E01, E10 | Reset synthetic state before case | Inject BATTERY_DEPLETED on None Run Troubleshoot on None | devices where {"active": false, "code": "GS-N002", "health": "OFFLINE", "id": "kitchen"} count = 1 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-060 | Connected Functional | diagnostics | Node fault LINK_LOSS maps to stable diagnostics and reboot recovery | E01, E10 | Reset synthetic state before case | Inject LINK_LOSS on None Run Troubleshoot on None Run Reboot on None | devices where {"active": true, "code": "GS-OK000", "health": "ACTIVE", "id": "kitchen"} count = 1 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-061 | Connected Functional | diagnostics | Node fault SENSOR_FAULT maps to stable diagnostics | E01, E10 | Reset synthetic state before case | Inject SENSOR_FAULT on None Run Troubleshoot on None | devices where {"active": true, "code": "GS-N004", "health": "DEGRADED", "id": "kitchen"} count = 1 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-062 | Connected Functional | diagnostics | Node fault OVER_TEMP maps to stable diagnostics | E01, E10 | Reset synthetic state before case | Inject OVER_TEMP on None Run Troubleshoot on None | devices where {"active": false, "code": "GS-N005", "health": "OFFLINE", "id": "kitchen"} count = 1 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-063 | Connected Functional | diagnostics | Node fault WATCHDOG maps to stable diagnostics and reboot recovery | E01, E10 | Reset synthetic state before case | Inject WATCHDOG on None Run Troubleshoot on None Run Reboot on None | devices where {"active": true, "code": "GS-OK000", "health": "ACTIVE", "id": "kitchen"} count = 1 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-064 | Connected Functional | diagnostics | Hub fault POWER_LOSS maps to stable diagnostics | E04, E10 | Reset synthetic state before case | Inject POWER_LOSS on None Run Troubleshoot on None | devices where {"active": false, "code": "GS-H001", "health": "OFFLINE", "id": "hub"} count = 1 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-065 | Connected Functional | diagnostics | Hub fault NODE_RADIO_FAILURE maps to stable diagnostics and reboot recovery | E04, E10 | Reset synthetic state before case | Inject NODE_RADIO_FAILURE on None Run Troubleshoot on None Run Reboot on None | devices where {"active": true, "code": "GS-OK000", "health": "ACTIVE", "id": "hub"} count = 1 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-066 | Connected Functional | diagnostics | Hub fault INTERNET_LOSS maps to stable diagnostics | E04, E10 | Reset synthetic state before case | Inject INTERNET_LOSS on None Run Troubleshoot on None | devices where {"active": true, "code": "GS-H003", "health": "DEGRADED", "id": "hub"} count = 1 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-067 | Connected Functional | diagnostics | Hub fault OVER_TEMP maps to stable diagnostics | E04, E10 | Reset synthetic state before case | Inject OVER_TEMP on None Run Troubleshoot on None | devices where {"active": false, "code": "GS-H004", "health": "OFFLINE", "id": "hub"} count = 1 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
FNC-068 | Connected Functional | diagnostics | Hub fault WATCHDOG maps to stable diagnostics and reboot recovery | E04, E10 | Reset synthetic state before case | Inject WATCHDOG on None Run Troubleshoot on None Run Reboot on None | devices where {"active": true, "code": "GS-OK000", "health": "ACTIVE", "id": "hub"} count = 1 | Automated + Manual | PASS | Not Run | tests/functional/scenario_catalog.json
DUM-001 | Dummy Sensor Stream | multi-event | Configured daytime inactivity triggers family check-in workflow |  | Fixture daytime_inactivity.json | Change household settings: {"daytime_inactivity_seconds": 300} Set local minute to 600 Advance simulated clock by 300 seconds | timeline where {"kind": "DAYTIME_INACTIVITY", "tone": "danger"} count = 1 incidents where {"kind": "DAYTIME_INACTIVITY", "state": "OPEN"} count = 1 | Automated | PASS | N/A | tests/fixtures/sensor_streams/daytime_inactivity.json
DUM-002 | Dummy Sensor Stream | multi-event | Late-night door stays open then closes |  | Fixture late_night_door.json | Inject DOOR_OPEN from entry (late-night) Advance simulated clock by 360 seconds Inject DOOR_CLOSED from entry | timeline where {"kind": "DOOR_LEFT_OPEN", "tone": "danger"} count = 1 home.latest_activity.kind = DOOR_CLOSED home.latest_activity.details.resolved_left_open = True | Automated | PASS | N/A | tests/fixtures/sensor_streams/late_night_door.json
DUM-003 | Dummy Sensor Stream | multi-event | Missing morning followed by later household activity |  | Fixture missing_then_recovery_activity.json | Advance simulated clock by 1300 seconds Inject MOTION from room1 Advance simulated clock by 120 seconds Inject MOTION from kitchen Inject DOOR_OPEN from entry | incidents where {"kind": "MISSING_MORNING_ACTIVITY"} count = 1 home.recent_events where {"kind": "MOTION"} count >= 2 home.recent_events where {"kind": "DOOR_OPEN"} count = 1 | Automated | PASS | N/A | tests/fixtures/sensor_streams/missing_then_recovery_activity.json
DUM-004 | Dummy Sensor Stream | multi-event | Normal morning kitchen and pooja activity |  | Fixture normal_morning.json | Inject MOTION from kitchen Advance simulated clock by 120 seconds Inject MOTION from pooja Advance simulated clock by 1180 seconds | incidents where {"kind": "MISSING_MORNING_ACTIVITY"} count = 0 simulation.reason = evidence_present | Automated | PASS | N/A | tests/fixtures/sensor_streams/normal_morning.json
DUM-005 | Dummy Sensor Stream | multi-event | Sensor activity during WAN loss is replayed after reconnect |  | Fixture offline_replay.json | Set WAN disabled Inject MOTION from kitchen Advance simulated clock by 120 seconds Set WAN enabled | timeline where {"kind": "MOTION"} count = 1 simulation.pending_cloud = 0 | Automated | PASS | N/A | tests/fixtures/sensor_streams/offline_replay.json
HTTP-001 | HTTP Integration | API/E2E | test_release_scenarios_through_http |  | Local lab build/server | python tests/simulation_http_test.py | Test assertion passes | Automated | PASS | N/A | tests/simulation_http_test.py
HTTP-002 | HTTP Integration | API/E2E | test_web_assets_and_reused_modules |  | Local lab build/server | python tests/simulation_http_test.py | Test assertion passes | Automated | PASS | N/A | tests/simulation_http_test.py
HTTP-003 | HTTP Integration | API/E2E | test_event_reaches_real_snapshot_api |  | Local lab build/server | python tests/simulation_http_test.py | Test assertion passes | Automated | PASS | N/A | tests/simulation_http_test.py
HTTP-004 | HTTP Integration | API/E2E | test_call_family_then_ok_remains_chronological_and_unresolved |  | Local lab build/server | python tests/simulation_http_test.py | Test assertion passes | Automated | PASS | N/A | tests/simulation_http_test.py
HTTP-005 | HTTP Integration | API/E2E | test_door_left_open_and_close_duration |  | Local lab build/server | python tests/simulation_http_test.py | Test assertion passes | Automated | PASS | N/A | tests/simulation_http_test.py
HTTP-006 | HTTP Integration | API/E2E | test_household_settings_are_versioned_and_change_door_policy |  | Local lab build/server | python tests/simulation_http_test.py | Test assertion passes | Automated | PASS | N/A | tests/simulation_http_test.py
HTTP-007 | HTTP Integration | API/E2E | test_daytime_inactivity_runs_through_rule_engine_and_backend |  | Local lab build/server | python tests/simulation_http_test.py | Test assertion passes | Automated | PASS | N/A | tests/simulation_http_test.py
HTTP-008 | HTTP Integration | API/E2E | test_wrong_sensor_event_combination_is_rejected |  | Local lab build/server | python tests/simulation_http_test.py | Test assertion passes | Automated | PASS | N/A | tests/simulation_http_test.py
HTTP-009 | HTTP Integration | API/E2E | test_privacy_toggle_is_not_a_simulation_event |  | Local lab build/server | python tests/simulation_http_test.py | Test assertion passes | Automated | PASS | N/A | tests/simulation_http_test.py
HTTP-010 | HTTP Integration | API/E2E | test_device_fault_maps_to_error_code |  | Local lab build/server | python tests/simulation_http_test.py | Test assertion passes | Automated | PASS | N/A | tests/simulation_http_test.py
HTTP-011 | HTTP Integration | API/E2E | test_browser_incident_actions_and_ownership |  | Local lab build/server | python tests/simulation_http_test.py | Test assertion passes | Automated | PASS | N/A | tests/simulation_http_test.py
HTTP-012 | HTTP Integration | API/E2E | test_unknown_actor_denied |  | Local lab build/server | python tests/simulation_http_test.py | Test assertion passes | Automated | PASS | N/A | tests/simulation_http_test.py
HTTP-013 | HTTP Integration | API/E2E | test_cross_origin_denied |  | Local lab build/server | python tests/simulation_http_test.py | Test assertion passes | Automated | PASS | N/A | tests/simulation_http_test.py
HTTP-014 | HTTP Integration | API/E2E | test_invalid_step_rejected_without_crash |  | Local lab build/server | python tests/simulation_http_test.py | Test assertion passes | Automated | PASS | N/A | tests/simulation_http_test.py
HTTP-015 | HTTP Integration | API/E2E | test_source_files_not_served |  | Local lab build/server | python tests/simulation_http_test.py | Test assertion passes | Automated | PASS | N/A | tests/simulation_http_test.py
HTTP-016 | HTTP Integration | API/E2E | test_offline_missing_intent_keeps_detection_time |  | Local lab build/server | python tests/simulation_http_test.py | Test assertion passes | Automated | PASS | N/A | tests/simulation_http_test.py
PY-001 | Python Backend/DB | component | test_B01_F01_membership_is_tenant_scoped |  | Host Python environment | make python-test | Unit/integration assertion passes | Automated | PASS | N/A | tests/python/test_backend.py
PY-002 | Python Backend/DB | component | test_B02_consent_withdrawal_enters_privacy |  | Host Python environment | make python-test | Unit/integration assertion passes | Automated | PASS | N/A | tests/python/test_backend.py
PY-003 | Python Backend/DB | component | test_B03_ingest_is_idempotent |  | Host Python environment | make python-test | Unit/integration assertion passes | Automated | PASS | N/A | tests/python/test_backend.py
PY-004 | Python Backend/DB | component | test_B04_B05_call_creates_one_incident_and_two_bounded_routes |  | Host Python environment | make python-test | Unit/integration assertion passes | Automated | PASS | N/A | tests/python/test_backend.py
PY-005 | Python Backend/DB | component | test_B04_claim_lease_prevents_double_ownership |  | Host Python environment | make python-test | Unit/integration assertion passes | Automated | PASS | N/A | tests/python/test_backend.py
PY-006 | Python Backend/DB | component | test_B06_config_version_and_device_binding |  | Host Python environment | make python-test | Unit/integration assertion passes | Automated | PASS | N/A | tests/python/test_backend.py
PY-007 | Python Backend/DB | component | test_B07_B08_snapshot_separates_activity_from_reachability |  | Host Python environment | make python-test | Unit/integration assertion passes | Automated | PASS | N/A | tests/python/test_backend.py
PY-008 | Python Backend/DB | component | test_test_alert_never_creates_production_incident |  | Host Python environment | make python-test | Unit/integration assertion passes | Automated | PASS | N/A | tests/python/test_backend.py
PY-009 | Python Backend/DB | component | test_daytime_inactivity_creates_one_checkin_incident_and_routes |  | Host Python environment | make python-test | Unit/integration assertion passes | Automated | PASS | N/A | tests/python/test_backend.py
PY-010 | Python Backend/DB | component | test_B05_F09_quiet_door_notice_is_opt_in_and_idempotent |  | Host Python environment | make python-test | Unit/integration assertion passes | Automated | PASS | N/A | tests/python/test_backend.py
PY-011 | Python Backend/DB | component | test_B05_F14_summary_is_opt_in_single_and_coverage_honest |  | Host Python environment | make python-test | Unit/integration assertion passes | Automated | PASS | N/A | tests/python/test_backend.py
PY-012 | Python Backend/DB | component | test_p0_tables_exist |  | Host Python environment | make python-test | Unit/integration assertion passes | Automated | PASS | N/A | tests/python/test_database_schema.py
PY-013 | Python Backend/DB | component | test_event_identity_suppresses_duplicates |  | Host Python environment | make python-test | Unit/integration assertion passes | Automated | PASS | N/A | tests/python/test_database_schema.py
PY-014 | Python Backend/DB | component | test_alert_stable_key_is_idempotent |  | Host Python environment | make python-test | Unit/integration assertion passes | Automated | PASS | N/A | tests/python/test_database_schema.py
PY-015 | Python Backend/DB | component | test_routine_window_is_persistable_for_reboot_recovery |  | Host Python environment | make python-test | Unit/integration assertion passes | Automated | PASS | N/A | tests/python/test_database_schema.py
PY-016 | Python Backend/DB | component | test_notification_job_idempotency_and_human_ack_are_separate |  | Host Python environment | make python-test | Unit/integration assertion passes | Automated | PASS | N/A | tests/python/test_database_schema.py
PY-017 | Python Backend/DB | component | test_device_health_is_not_resident_activity |  | Host Python environment | make python-test | Unit/integration assertion passes | Automated | PASS | N/A | tests/python/test_database_schema.py
PY-018 | Python Backend/DB | component | test_production_keeps_error_and_filters_trace |  | Host Python environment | make python-test | Unit/integration assertion passes | Automated | PASS | N/A | tests/python/test_logging.py
PY-019 | Python Backend/DB | component | test_development_trace_records_flow |  | Host Python environment | make python-test | Unit/integration assertion passes | Automated | PASS | N/A | tests/python/test_logging.py
PY-020 | Python Backend/DB | component | test_feature_flags_are_safe_by_default |  | Host Python environment | make python-test | Unit/integration assertion passes | Automated | PASS | N/A | tests/python/test_logging.py
PY-021 | Python Backend/DB | component | test_catalog_has_required_categories_and_unique_ids |  | Host Python environment | make python-test | Unit/integration assertion passes | Automated | PASS | N/A | tests/python/test_validation_framework.py
PY-022 | Python Backend/DB | component | test_all_fault_codes_have_scenarios |  | Host Python environment | make python-test | Unit/integration assertion passes | Automated | PASS | N/A | tests/python/test_validation_framework.py
PY-023 | Python Backend/DB | component | test_manual_plan_is_generated |  | Host Python environment | make python-test | Unit/integration assertion passes | Automated | PASS | N/A | tests/python/test_validation_framework.py
PY-024 | Python Backend/DB | component | test_dummy_streams_exist |  | Host Python environment | make python-test | Unit/integration assertion passes | Automated | PASS | N/A | tests/python/test_validation_framework.py
JS-001 | JavaScript App | component | A01 requires resident consent and distinct backup |  | Node test runner | make app-test | App semantic assertion passes | Automated | PASS | N/A | tests/js/app.test.mjs
JS-002 | JavaScript App | component | A01 installation gate enumerates missing device tests |  | Node test runner | make app-test | App semantic assertion passes | Automated | PASS | N/A | tests/js/app.test.mjs
JS-003 | JavaScript App | component | A02 never converts absent evidence into wellbeing |  | Node test runner | make app-test | App semantic assertion passes | Automated | PASS | N/A | tests/js/app.test.mjs
JS-004 | JavaScript App | component | A02 presents exact activity meaning and age |  | Node test runner | make app-test | App semantic assertion passes | Automated | PASS | N/A | tests/js/app.test.mjs
JS-005 | JavaScript App | component | A02 presents daytime inactivity as a concern |  | Node test runner | make app-test | App semantic assertion passes | Automated | PASS | N/A | tests/js/app.test.mjs
JS-006 | JavaScript App | component | A03 produces versioned routine and household-policy config |  | Node test runner | make app-test | App semantic assertion passes | Automated | PASS | N/A | tests/js/app.test.mjs
JS-007 | JavaScript App | component | A04 prevents action when another caregiver owns a live lease |  | Node test runner | make app-test | App semantic assertion passes | Automated | PASS | N/A | tests/js/app.test.mjs
JS-008 | JavaScript App | component | A05 cache rejects older versions and reports push gaps |  | Node test runner | make app-test | App semantic assertion passes | Automated | PASS | N/A | tests/js/app.test.mjs
JS-009 | JavaScript App | component | A05 logger retains errors and applies the build trace gate |  | Node test runner | make app-test | App semantic assertion passes | Automated | PASS | N/A | tests/js/app.test.mjs
JS-010 | JavaScript App | component | feature flags keep unfinished capabilities disabled |  | Node test runner | make app-test | App semantic assertion passes | Automated | PASS | N/A | tests/js/app.test.mjs
CPP-001 | C++ Unit/Component | component | initial PIR sample must not emit |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-002 | C++ Unit/Component | component | edge must debounce |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-003 | C++ Unit/Component | component | stable PIR rise must emit motion |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-004 | C++ Unit/Component | component | PIR inactive edge has no business event |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-005 | C++ Unit/Component | component | business event persists |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-006 | C++ Unit/Component | component | volatile ack cannot retire business event |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-007 | C++ Unit/Component | component | durable ack retires event |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-008 | C++ Unit/Component | component | radio queue accepts event |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-009 | C++ Unit/Component | component | queued event is due immediately |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-010 | C++ Unit/Component | component | radio preserves business event on volatile ack |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-011 | C++ Unit/Component | component | radio retires durable ack |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-012 | C++ Unit/Component | component | input-less config is rejected |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-013 | C++ Unit/Component | component | valid node config applies |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-014 | C++ Unit/Component | component | stale version is rejected |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-015 | C++ Unit/Component | component | physical service window is bounded and open |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-016 | C++ Unit/Component | component | service window closes |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-017 | C++ Unit/Component | component | calibrated low battery classification |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-018 | C++ Unit/Component | component | uncalibrated voltage stays unknown |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-019 | C++ Unit/Component | component | pending retry shortens wake interval |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-020 | C++ Unit/Component | component | node runtime persists before transmit |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-021 | C++ Unit/Component | component | node runtime exposes due transmission |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-022 | C++ Unit/Component | component | node runtime retires durable ack |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-023 | C++ Unit/Component | component | authorized packet copied |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-024 | C++ Unit/Component | component | state task receives copied packet |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-025 | C++ Unit/Component | component | unknown peer rejected |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-026 | C++ Unit/Component | component | journal stores event |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-027 | C++ Unit/Component | component | journal deduplicates event |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-028 | C++ Unit/Component | component | unanchored clock blocks absence |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-029 | C++ Unit/Component | component | trusted bounded clock permits absence evaluation |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-030 | C++ Unit/Component | component | unseen node means unknown coverage |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-031 | C++ Unit/Component | component | fresh required node covers window |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-032 | C++ Unit/Component | component | expired lease becomes unknown |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-033 | C++ Unit/Component | component | activity suppresses missing routine incident |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-034 | C++ Unit/Component | component | covered window without evidence creates incident |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-035 | C++ Unit/Component | component | stable window creates one incident |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-036 | C++ Unit/Component | component | coverage unknown never becomes confident inactivity |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-037 | C++ Unit/Component | component | privacy suppresses passive incident |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-038 | C++ Unit/Component | component | call button produces explicit action |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-039 | C++ Unit/Component | component | offline feedback is explicit |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-040 | C++ Unit/Component | component | valid home config applies |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-041 | C++ Unit/Component | component | same config version is rejected |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-042 | C++ Unit/Component | component | contact requests are replayed first |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-043 | C++ Unit/Component | component | application commit ack retires outbox item |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-044 | C++ Unit/Component | component | runtime callback admits known node |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-045 | C++ Unit/Component | component | state owner commits before durable ack |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-046 | C++ Unit/Component | component | runtime routes committed event to rules |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-047 | C++ Unit/Component | component | node heartbeat interval is frozen at 60 seconds |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-048 | C++ Unit/Component | component | three missed heartbeats plus grace means offline |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-049 | C++ Unit/Component | component | bounded retry schedule is shared by protocol code |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-050 | C++ Unit/Component | component | canonical node event records before transmission |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-051 | C++ Unit/Component | component | node event carries sensor type and RSSI independently of GPIO |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-052 | C++ Unit/Component | component | typed node wire message preserves canonical protocol fields |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-053 | C++ Unit/Component | component | hub adapter converts canonical wire message into the same generic DomainEvent |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-054 | C++ Unit/Component | component | typed durable ACK preserves the node event identity |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-055 | C++ Unit/Component | component | door opening during quiet hours is a pure rule decision |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-056 | C++ Unit/Component | component | door open for five minutes creates a rule signal |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-057 | C++ Unit/Component | component | door-left-open signal is latched and not duplicated |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-058 | C++ Unit/Component | component | door close resolves prior left-open state and preserves duration |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-059 | C++ Unit/Component | component | daytime no-activity threshold creates a check-in rule signal |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-060 | C++ Unit/Component | component | daytime inactivity is not repeatedly emitted until new activity |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-061 | C++ Unit/Component | component | new generic activity rearms the inactivity rule |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-062 | C++ Unit/Component | component | no-activity timer never turns unavailable sensor coverage into an inactivity concern |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-063 | C++ Unit/Component | component | daytime inactivity works even when no activity event has occurred since monitoring began |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-064 | C++ Unit/Component | component | quiet-hour concern is suppressed while monitoring mode is away |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-065 | C++ Unit/Component | component | quiet-hour window includes 01:30 |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-066 | C++ Unit/Component | component | quiet-hour window excludes daytime |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-067 | C++ Unit/Component | component | time windows may cross midnight |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-068 | C++ Unit/Component | component | hub accepts the canonical node message and converts it to a generic event |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-069 | C++ Unit/Component | component | hub adapter feeds generic events into the hardware-independent rule engine |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-070 | C++ Unit/Component | component | credential reference installs |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-071 | C++ Unit/Component | component | credential rollback rejected |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-072 | C++ Unit/Component | component | credential can be revoked |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-073 | C++ Unit/Component | component | valid signed manifest policy accepts |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-074 | C++ Unit/Component | component | wrong board manifest rejected |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-075 | C++ Unit/Component | component | firmware rollback rejected |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-076 | C++ Unit/Component | component | ERROR logging is always compiled |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-077 | C++ Unit/Component | component | TRACE logging is enabled in development build |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-078 | C++ Unit/Component | component | TRACE logging compiles out in production build |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-079 | C++ Unit/Component | component | morning flag maps to build |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-080 | C++ Unit/Component | component | P1 flag maps to build |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
CPP-081 | C++ Unit/Component | component | flag names are stable |  | Host C++ build | make cpp-test | check() assertion passes | Automated | PASS* | N/A | tests/cpp/test_main.cpp |  |  | *81 source checks; 80 execute in one trace profile because TRACE-on/off branch is conditional.
FEAT-001 | Feature Matrix | build variant | P0 default features |  | Morning=1, Call=1, Offline=1 | Build simulator with feature flags | Build and intended feature behavior pass | Automated | PASS | N/A | tools/validation/release_gate.py
FEAT-002 | Feature Matrix | build variant | Morning routine disabled |  | Morning=0 | Build simulator with feature flags | Build and intended feature behavior pass | Automated | PASS | N/A | tools/validation/release_gate.py
FEAT-003 | Feature Matrix | build variant | Call Family disabled |  | Call=0 | Build simulator with feature flags | Build and intended feature behavior pass | Automated | PASS | N/A | tools/validation/release_gate.py
FEAT-004 | Feature Matrix | build variant | Local offline disabled |  | Offline=0 | Build simulator with feature flags | Build and intended feature behavior pass | Automated | PASS | N/A | tools/validation/release_gate.py
PROD-001 | Product Profile | build | Base product profile |  | PRODUCT=base | make product-test PRODUCT=base | Profile tests pass | Automated | PASS | N/A | tests/cpp/test_product.cpp
PROD-002 | Product Profile | build | AI product profile compatibility |  | PRODUCT=ai | make product-test PRODUCT=ai | Profile tests pass | Automated | PASS | N/A | tests/cpp/test_product.cpp
UI-001 | Manual Browser/PWA | visual/usability | I am OK is visually positive/green and includes elapsed time |  | Run local lab in target browser | Follow Manual UI Checks sheet | Visual/usability criterion satisfied | Manual | MANUAL_REQUIRED | Not Run | tests/MANUAL_FUNCTIONAL_VALIDATION.md
UI-002 | Manual Browser/PWA | visual/usability | Unexpected/concern events are visually distinct and are not communicated by color alone |  | Run local lab in target browser | Follow Manual UI Checks sheet | Visual/usability criterion satisfied | Manual | MANUAL_REQUIRED | Not Run | tests/MANUAL_FUNCTIONAL_VALIDATION.md
UI-003 | Manual Browser/PWA | visual/usability | Active/degraded/offline device states have text labels as well as colored status circles |  | Run local lab in target browser | Follow Manual UI Checks sheet | Visual/usability criterion satisfied | Manual | MANUAL_REQUIRED | Not Run | tests/MANUAL_FUNCTIONAL_VALIDATION.md
UI-004 | Manual Browser/PWA | visual/usability | 390 px mobile viewport has no horizontal overflow and primary controls remain usable |  | Run local lab in target browser | Follow Manual UI Checks sheet | Visual/usability criterion satisfied | Manual | MANUAL_REQUIRED | Not Run | tests/MANUAL_FUNCTIONAL_VALIDATION.md
UI-005 | Manual Browser/PWA | visual/usability | Family/caregiver timeline is newest-first and unresolved missing-morning/call incidents remain visible |  | Run local lab in target browser | Follow Manual UI Checks sheet | Visual/usability criterion satisfied | Manual | MANUAL_REQUIRED | Not Run | tests/MANUAL_FUNCTIONAL_VALIDATION.md
UI-006 | Manual Browser/PWA | visual/usability | Settings values reload after Save and display the new configuration version |  | Run local lab in target browser | Follow Manual UI Checks sheet | Visual/usability criterion satisfied | Manual | MANUAL_REQUIRED | Not Run | tests/MANUAL_FUNCTIONAL_VALIDATION.md
UI-007 | Manual Browser/PWA | visual/usability | No Privacy ON/OFF control is present in normal household Settings |  | Run local lab in target browser | Follow Manual UI Checks sheet | Visual/usability criterion satisfied | Manual | MANUAL_REQUIRED | Not Run | tests/MANUAL_FUNCTIONAL_VALIDATION.md
HIL-001 | Hardware/HIL | pending | Real PIR/reed/buttons |  | Physical/integration environment required | Debounce, stuck input, electrical noise, mounting, field wiring, button response latency | Mandatory before unattended pilot | Manual/HIL | PENDING | Not Run | Untested & HIL sheet
HIL-002 | Hardware/HIL | pending | ESP-NOW RF/RSSI/offline timing |  | Physical/integration environment required | Real packet loss, channel coexistence/interference/range, RSSI distribution, missed heartbeats and reconnect | Mandatory before unattended pilot | Manual/HIL | PENDING | Not Run | Untested & HIL sheet
HIL-003 | Hardware/HIL | pending | Battery/runtime/charging/UPS |  | Physical/integration environment required | ADC calibration, runtime, charge behavior, brown-out under load, UPS handover, low-battery thresholds | Mandatory before unattended pilot | Manual/HIL | PENDING | Not Run | Untested & HIL sheet
HIL-004 | Hardware/HIL | pending | Brown-out/reset/watchdog |  | Physical/integration environment required | Actual reset reasons, reboot recovery, watchdog behavior and persistent state on target boards | Mandatory before unattended pilot | Manual/HIL | PENDING | Not Run | Untested & HIL sheet
HIL-005 | Hardware/HIL | pending | Flash persistence/wear |  | Physical/integration environment required | Power-loss atomicity, queue retention, compaction, overflow, wear and durable recovery | Mandatory before unattended pilot | Manual/HIL | PENDING | Not Run | Untested & HIL sheet
HIL-006 | Hardware/HIL | pending | OTA signing/rollback |  | Physical/integration environment required | Real signature/hash, wrong-board image, interrupted update, rollback and first-boot recovery | Mandatory before unattended pilot | Manual/HIL | PENDING | Not Run | Untested & HIL sheet
HIL-007 | Hardware/HIL | pending | Temperature telemetry |  | Physical/integration environment required | Real sensor/MCU temperature thresholds and false-positive behavior | Mandatory before unattended pilot | Manual/HIL | PENDING | Not Run | Untested & HIL sheet
HIL-008 | External integration | pending | Real notification provider |  | Physical/integration environment required | Provider failure/timeout/receipt, duplicate delivery, phone receipt/background restrictions/retry | Mandatory before unattended pilot | Manual/HIL | PENDING | Not Run | Untested & HIL sheet
HIL-009 | Pilot/HIL | pending | Installed-home coverage |  | Physical/integration environment required | Room placement, dead zones, sensor line-of-sight, router/power conditions, full routine-window coverage | Mandatory before unattended pilot | Manual/HIL | PENDING | Not Run | Untested & HIL sheet
GAP-001 | Recommended gap | pending | Long-duration soak |  | Physical/integration environment required | 24 h / 72 h / multi-week repeated events, retries and storage pressure | Recommended before pilot | Manual/HIL | NOT EXHAUSTIVE | Not Run | Untested & HIL sheet
GAP-002 | Recommended gap | pending | High-rate bursts and queue saturation |  | Physical/integration environment required | Realistic FreeRTOS scheduling, queue pressure and event bursts on exact ESP32 variants | Recommended before pilot | Manual/HIL | NOT EXHAUSTIVE | Not Run | Untested & HIL sheet
GAP-003 | Recommended gap | pending | Network jitter/reordering/partial loss |  | Physical/integration environment required | Multi-boundary jitter, reordering and loss beyond deterministic modeled cases | Recommended before pilot | Manual/HIL | NOT EXHAUSTIVE | Not Run | Untested & HIL sheet
GAP-004 | Recommended gap | pending | Production security/penetration |  | Physical/integration environment required | TLS, production authN/authZ, credential rotation/revocation, endpoint and log review | Mandatory before production | Manual/HIL | NOT EXHAUSTIVE | Not Run | Untested & HIL sheet
GAP-005 | Recommended gap | pending | Target resource/performance budgets |  | Physical/integration environment required | CPU, RAM, flash, wake time, Wi-Fi/ESP-NOW coexistence and battery current | Mandatory before pilot | Manual/HIL | NOT EXHAUSTIVE | Not Run | Untested & HIL sheet
GAP-006 | Recommended gap | pending | Accessibility/usability on target devices |  | Physical/integration environment required | Target caregivers/residents, Android/browser matrix and accessibility comprehension | Recommended before pilot | Manual/HIL | NOT EXHAUSTIVE | Not Run | Untested & HIL sheet
GAP-007 | Recommended gap | pending | Persistent backend DB operations |  | Physical/integration environment required | Concurrency, crash consistency, migrations, upgrade/rollback, backup/restore | Before production backend | Manual/HIL | NOT EXHAUSTIVE | Not Run | Untested & HIL sheet
GAP-008 | Recommended gap | pending | Timezone/DST exhaustive coverage |  | Physical/integration environment required | Non-India deployments, DST transitions, clock rollback/uncertainty boundaries | Before non-India rollout | Manual/HIL | NOT EXHAUSTIVE | Not Run | Untested & HIL sheet

## Functional Scenarios
Manual ID | Scenario ID | Category | Title | Requirements | Steps | Expected / Assertions | Automation | Release | Current Status | Manual Result | Defect ID | Notes
M001 | motion-room1-visible | expected | Room 1 motion is preserved as exact positive activity | F05, F11 | 1. Inject MOTION from room1 | 1. home.latest_activity.kind = MOTION 2. home.latest_activity.location = room1 3. home.latest_activity.tone = positive | Automated + Manual | v1.5.4 | PASS | Not Run
M002 | motion-kitchen-visible | expected | Kitchen motion is preserved as exact positive activity | F05, F11 | 1. Inject MOTION from kitchen | 1. home.latest_activity.location = kitchen 2. home.latest_activity.tone = positive | Automated + Manual | v1.5.4 | PASS | Not Run
M003 | motion-pooja-visible | expected | Pooja motion is preserved as exact positive activity | F05, F11 | 1. Inject MOTION from pooja | 1. home.latest_activity.location = pooja 2. home.latest_activity.tone = positive | Automated + Manual | v1.5.4 | PASS | Not Run
M004 | door-open-daytime | expected | Normal daytime door opening is green and explicit | F09, F11 | 1. Inject DOOR_OPEN from entry | 1. home.latest_activity.kind = DOOR_OPEN 2. home.latest_activity.tone = positive 3. home.latest_activity.details.unexpected = False | Automated + Manual | v1.5.4 | PASS | Not Run
M005 | door-open-close-order | expected | Door open and close remain chronological and explicit | F09, F11 | 1. Inject DOOR_OPEN from entry 2. Advance simulated clock by 60 seconds 3. Inject DOOR_CLOSED from entry | 1. home.recent_events starts with ['DOOR_CLOSED', 'DOOR_OPEN'] by kind 2. home.door_status.state = CLOSED | Automated + Manual | v1.5.4 | PASS | Not Run
M006 | resident-ok-green | expected | I am OK remains a distinct green self-check-in | F06, F11 | 1. Inject OK_PRESSED from room1 | 1. home.latest_activity.kind = OK_PRESSED 2. home.latest_activity.tone = positive | Automated + Manual | v1.5.4 | PASS | Not Run
M007 | call-family-opens-workflow | expected | Call Family opens exactly one incident and two routes | F07, F13 | 1. Inject CALL_FAMILY from room1 | 1. incidents where {"kind": "CALL_FAMILY", "state": "OPEN"} count = 1 2. notifications where {} count = 2 | Automated + Manual | v1.5.4 | PASS | Not Run
M008 | call-then-ok-keeps-call | expected | I am OK after Call Family is newer but does not resolve the request | F06, F07, F11 | 1. Inject CALL_FAMILY from room1 2. Advance simulated clock by 60 seconds 3. Inject OK_PRESSED from room1 | 1. home.recent_events starts with ['OK_PRESSED', 'CALL_FAMILY'] by kind 2. incidents where {"kind": "CALL_FAMILY", "state": "OPEN"} count = 1 | Automated + Manual | v1.5.4 | PASS | Not Run
M009 | post-missing-activity-visible | expected | Later activities remain visible after missing-morning alert | F08, F11 | 1. Advance simulated clock by 1300 seconds 2. Inject MOTION from room1 3. Advance simulated clock by 60 seconds 4. Inject MOTION from kitchen 5. Inject DOOR_OPEN from entry | 1. incidents where {"kind": "MISSING_MORNING_ACTIVITY"} count = 1 2. home.recent_events where {"kind": "MOTION"} count >= 2 3. home.recent_events where {"kind": "DOOR_OPEN"} count = 1 | Automated + Manual | v1.5.4 | PASS | Not Run
M010 | morning-missing-covered | morning | Covered morning with no evidence creates one concern | F08 | 1. Advance simulated clock by 1300 seconds | 1. simulation.reason = no_qualifying_evidence 2. incidents where {"kind": "MISSING_MORNING_ACTIVITY"} count = 1 3. notifications where {} count = 2 | Automated + Manual | v1.5.4 | PASS | Not Run
M011 | morning-kitchen-qualifies | morning | Kitchen motion satisfies morning routine | F05, F08 | 1. Inject MOTION from kitchen 2. Advance simulated clock by 1300 seconds | 1. simulation.reason = evidence_present 2. incidents where {"kind": "MISSING_MORNING_ACTIVITY"} count = 0 | Automated + Manual | v1.5.4 | PASS | Not Run
M012 | morning-pooja-qualifies | morning | Pooja motion satisfies morning routine | F05, F08 | 1. Inject MOTION from pooja 2. Advance simulated clock by 1300 seconds | 1. simulation.reason = evidence_present 2. incidents where {"kind": "MISSING_MORNING_ACTIVITY"} count = 0 | Automated + Manual | v1.5.4 | PASS | Not Run
M013 | morning-room1-not-qualifying | morning | Room 1 motion does not silently satisfy kitchen/pooja morning policy | F04, F08 | 1. Inject MOTION from room1 2. Advance simulated clock by 1300 seconds | 1. incidents where {"kind": "MISSING_MORNING_ACTIVITY"} count = 1 | Automated + Manual | v1.5.4 | PASS | Not Run
M014 | morning-door-not-qualifying | morning | Main-door activity does not silently satisfy kitchen/pooja morning policy | F04, F08 | 1. Inject DOOR_OPEN from entry 2. Advance simulated clock by 1300 seconds | 1. incidents where {"kind": "MISSING_MORNING_ACTIVITY"} count = 1 | Automated + Manual | v1.5.4 | PASS | Not Run
M015 | morning-ok-qualifies | morning | Explicit I am OK satisfies morning check-in independently of PIR | F06, F08 | 1. Inject OK_PRESSED from room1 2. Advance simulated clock by 1300 seconds | 1. simulation.explicit_ok is true/non-empty 2. incidents where {"kind": "MISSING_MORNING_ACTIVITY"} count = 0 | Automated + Manual | v1.5.4 | PASS | Not Run
M016 | morning-coverage-gap-suppresses | morning | Missing sensor coverage suppresses inactivity interpretation | E01, F08 | 1. {"action": "node", "enabled": false, "node": "kitchen"} 2. Advance simulated clock by 1300 seconds | 1. simulation.reason = coverage_unknown 2. incidents where {"kind": "MISSING_MORNING_ACTIVITY"} count = 0 | Automated + Manual | v1.5.4 | PASS | Not Run
M017 | morning-untrusted-clock-suppresses | morning | Untrusted clock suppresses time-based morning concern | E06, F08 | 1. Set trusted clock disabled 2. Advance simulated clock by 1300 seconds | 1. simulation.reason = time_untrusted 2. incidents where {"kind": "MISSING_MORNING_ACTIVITY"} count = 0 | Automated + Manual | v1.5.4 | PASS | Not Run
M018 | morning-wan-offline-replay | morning | Morning concern detected offline replays with original detection time | E03, F08 | 1. Set WAN disabled 2. Advance simulated clock by 1300 seconds 3. Advance simulated clock by 60 seconds 4. Set WAN enabled | 1. incidents where {"kind": "MISSING_MORNING_ACTIVITY"} count = 1 2. timeline where {"kind": "MISSING_MORNING_ACTIVITY", "occurred_at": 2300} count = 1 | Automated + Manual | v1.5.4 | PASS | Not Run
M019 | morning-repeat-deadline-idempotent | morning | Repeated deadline evaluation does not create duplicate missing incident | E02, F08 | 1. Advance simulated clock by 1300 seconds 2. {"action": "deadline"} 3. {"action": "deadline"} | 1. incidents where {"kind": "MISSING_MORNING_ACTIVITY"} count = 1 | Automated + Manual | v1.5.4 | PASS | Not Run
M020 | door-late-night-red | door | Door opening in configured quiet hours is unexpected/red | F09 | 1. Inject DOOR_OPEN from entry (late-night) | 1. home.latest_activity.details.unexpected = True 2. home.latest_activity.tone = danger | Automated + Manual | v1.5.4 | PASS | Not Run
M021 | door-quiet-rule-disabled | door | Quiet-hour door opening is normal when the household disables that rule | F09, E07 | 1. Change household settings: {"quiet_hours_enabled": false} 2. Inject DOOR_OPEN from entry (late-night) | 1. home.latest_activity.details.unexpected = False 2. home.latest_activity.tone = positive | Automated + Manual | v1.5.4 | PASS | Not Run
M022 | door-late-night-away-suppressed | door | Late-night door concern is suppressed in AWAY mode | F09, F10 | 1. Set home mode to AWAY 2. Inject DOOR_OPEN from entry (late-night) | 1. home.latest_activity.details.unexpected = False 2. home.mode = AWAY | Automated + Manual | v1.5.4 | PASS | Not Run
M023 | door-late-night-paused-suppressed | door | Late-night door concern is suppressed in PAUSED mode | F09, F10 | 1. Set home mode to PAUSED 2. Inject DOOR_OPEN from entry (late-night) | 1. home.latest_activity.details.unexpected = False 2. home.mode = PAUSED | Automated + Manual | v1.5.4 | PASS | Not Run
M024 | door-late-night-visitor-suppressed | door | Late-night door concern is suppressed in VISITOR mode | F09, F10 | 1. Set home mode to VISITOR 2. Inject DOOR_OPEN from entry (late-night) | 1. home.latest_activity.details.unexpected = False 2. home.mode = VISITOR | Automated + Manual | v1.5.4 | PASS | Not Run
M025 | door-left-open-before-threshold | door | Door left open before threshold does not warn | F09 | 1. Inject DOOR_OPEN from entry 2. Advance simulated clock by 299 seconds | 1. timeline where {"kind": "DOOR_LEFT_OPEN"} count = 0 2. home.door_status.left_open = False | Automated + Manual | v1.5.4 | PASS | Not Run
M026 | door-left-open-at-threshold | door | Door left open at threshold creates one red warning | F09 | 1. Inject DOOR_OPEN from entry 2. Advance simulated clock by 300 seconds | 1. timeline where {"kind": "DOOR_LEFT_OPEN", "tone": "danger"} count = 1 2. home.door_status.left_open = True | Automated + Manual | v1.5.4 | PASS | Not Run
M027 | door-close-before-threshold | door | Door closed before threshold remains normal | F09 | 1. Inject DOOR_OPEN from entry 2. Advance simulated clock by 240 seconds 3. Inject DOOR_CLOSED from entry | 1. timeline where {"kind": "DOOR_LEFT_OPEN"} count = 0 2. home.latest_activity.kind = DOOR_CLOSED 3. home.latest_activity.tone = positive | Automated + Manual | v1.5.4 | PASS | Not Run
M028 | door-close-after-warning | door | Closing a left-open door clears current condition and preserves duration | F09 | 1. Inject DOOR_OPEN from entry 2. Advance simulated clock by 360 seconds 3. Inject DOOR_CLOSED from entry | 1. timeline where {"kind": "DOOR_LEFT_OPEN"} count = 1 2. home.latest_activity.details.resolved_left_open = True 3. {"ge": 360, "path": "home.latest_activity.details.open_duration_s"} 4. home.door_status.state = CLOSED | Automated + Manual | v1.5.4 | PASS | Not Run
M029 | door-close-without-open | door | Standalone close state does not invent a left-open warning | F09 | 1. Inject DOOR_CLOSED from entry | 1. timeline where {"kind": "DOOR_LEFT_OPEN"} count = 0 2. home.door_status.state = CLOSED | Automated + Manual | v1.5.4 | PASS | Not Run
M030 | door-configurable-threshold | door | Door-left-open threshold follows household configuration | F09, E07 | 1. Change household settings: {"door_open_timeout_seconds": 120} 2. Inject DOOR_OPEN from entry 3. Advance simulated clock by 119 seconds 4. Advance simulated clock by 1 seconds | 1. timeline where {"kind": "DOOR_LEFT_OPEN"} count = 1 2. home.door_status.left_open = True | Automated + Manual | v1.5.4 | PASS | Not Run
M031 | inactivity-before-threshold | inactivity | No activity before configured threshold does not alert | F11 | 1. Change household settings: {"daytime_inactivity_seconds": 300} 2. Set local minute to 600 3. Advance simulated clock by 299 seconds | 1. timeline where {"kind": "DAYTIME_INACTIVITY"} count = 0 2. incidents where {"kind": "DAYTIME_INACTIVITY"} count = 0 | Automated + Manual | v1.5.4 | PASS | Not Run
M032 | inactivity-at-threshold | inactivity | No activity at configured threshold opens check-in workflow | F11, F12 | 1. Change household settings: {"daytime_inactivity_seconds": 300} 2. Set local minute to 600 3. Advance simulated clock by 300 seconds | 1. timeline where {"kind": "DAYTIME_INACTIVITY", "tone": "danger"} count = 1 2. incidents where {"kind": "DAYTIME_INACTIVITY", "state": "OPEN"} count = 1 3. notifications where {} count = 2 | Automated + Manual | v1.5.4 | PASS | Not Run
M033 | inactivity-motion-rearms | inactivity | Activity resets daytime inactivity timer | F05 | 1. Change household settings: {"daytime_inactivity_seconds": 300} 2. Set local minute to 600 3. Advance simulated clock by 240 seconds 4. Inject MOTION from room1 5. Advance simulated clock by 240 seconds | 1. timeline where {"kind": "DAYTIME_INACTIVITY"} count = 0 | Automated + Manual | v1.5.4 | PASS | Not Run
M034 | inactivity-disabled | inactivity | Disabled daytime inactivity policy produces no concern | E07 | 1. Change household settings: {"daytime_inactivity_enabled": false, "daytime_inactivity_seconds": 300} 2. Set local minute to 600 3. Advance simulated clock by 600 seconds | 1. timeline where {"kind": "DAYTIME_INACTIVITY"} count = 0 | Automated + Manual | v1.5.4 | PASS | Not Run
M035 | inactivity-away-suppressed | inactivity | Daytime inactivity is suppressed in AWAY mode | F10 | 1. Change household settings: {"daytime_inactivity_seconds": 300} 2. Set local minute to 600 3. Set home mode to AWAY 4. Advance simulated clock by 300 seconds | 1. timeline where {"kind": "DAYTIME_INACTIVITY"} count = 0 2. home.mode = AWAY | Automated + Manual | v1.5.4 | PASS | Not Run
M036 | inactivity-paused-suppressed | inactivity | Daytime inactivity is suppressed in PAUSED mode | F10 | 1. Change household settings: {"daytime_inactivity_seconds": 300} 2. Set local minute to 600 3. Set home mode to PAUSED 4. Advance simulated clock by 300 seconds | 1. timeline where {"kind": "DAYTIME_INACTIVITY"} count = 0 2. home.mode = PAUSED | Automated + Manual | v1.5.4 | PASS | Not Run
M037 | inactivity-visitor-suppressed | inactivity | Daytime inactivity is suppressed in VISITOR mode | F10 | 1. Change household settings: {"daytime_inactivity_seconds": 300} 2. Set local minute to 600 3. Set home mode to VISITOR 4. Advance simulated clock by 300 seconds | 1. timeline where {"kind": "DAYTIME_INACTIVITY"} count = 0 2. home.mode = VISITOR | Automated + Manual | v1.5.4 | PASS | Not Run
M038 | inactivity-coverage-gap-suppressed | inactivity | Daytime inactivity is suppressed when observation coverage is unavailable | E01 | 1. Change household settings: {"daytime_inactivity_seconds": 300} 2. Set local minute to 600 3. {"action": "node", "enabled": false, "node": "kitchen"} 4. Advance simulated clock by 300 seconds | 1. timeline where {"kind": "DAYTIME_INACTIVITY"} count = 0 | Automated + Manual | v1.5.4 | PASS | Not Run
M039 | inactivity-clock-untrusted-suppressed | inactivity | Daytime inactivity is suppressed when time is untrusted | E06 | 1. Change household settings: {"daytime_inactivity_seconds": 300} 2. Set local minute to 600 3. Set trusted clock disabled 4. Advance simulated clock by 300 seconds | 1. timeline where {"kind": "DAYTIME_INACTIVITY"} count = 0 | Automated + Manual | v1.5.4 | PASS | Not Run
M040 | inactivity-outside-daytime-window | inactivity | Daytime inactivity does not fire outside configured daytime window | E06 | 1. Change household settings: {"daytime_inactivity_seconds": 300} 2. Set local minute to 1380 3. Advance simulated clock by 300 seconds | 1. timeline where {"kind": "DAYTIME_INACTIVITY"} count = 0 | Automated + Manual | v1.5.4 | PASS | Not Run
M041 | wan-loss-local-progress | transport | WAN loss keeps local evidence while backend view is stale | E03, E04 | 1. Set WAN disabled 2. Inject MOTION from kitchen 3. Advance simulated clock by 240 seconds | 1. simulation.activity_seen is true/non-empty 2. {"gt": 0, "path": "simulation.pending_cloud"} 3. home.hub_reachable = False 4. timeline where {"kind": "MOTION"} count = 0 | Automated + Manual | v1.5.4 | PASS | Not Run
M042 | wan-reconnect-replays | transport | WAN reconnect replays pending event exactly once | E02, E03 | 1. Set WAN disabled 2. Inject MOTION from kitchen 3. Set WAN enabled | 1. simulation.pending_cloud = 0 2. timeline where {"kind": "MOTION"} count = 1 | Automated + Manual | v1.5.4 | PASS | Not Run
M043 | node-link-replay | transport | Node link recovery replays retained event exactly once | E02 | 1. {"action": "node", "enabled": false, "node": "kitchen"} 2. Inject MOTION from kitchen 3. {"action": "node", "enabled": true, "node": "kitchen"} | 1. timeline where {"kind": "MOTION"} count = 1 2. simulation.nodes.1.retained = 0 | Automated + Manual | v1.5.4 | PASS | Not Run
M044 | duplicate-event-backend-idempotent | transport | Duplicate radio replay is stored once by backend | E02 | 1. Inject MOTION from kitchen 2. {"action": "duplicate"} | 1. timeline where {"kind": "MOTION"} count = 1 | Automated + Manual | v1.5.4 | PASS | Not Run
M045 | call-family-offline-replay | transport | Call Family survives WAN outage and opens one incident on reconnect | E03, F07 | 1. Set WAN disabled 2. Inject CALL_FAMILY from room1 3. Set WAN enabled | 1. incidents where {"kind": "CALL_FAMILY"} count = 1 | Automated + Manual | v1.5.4 | PASS | Not Run
M046 | provider-acceptance-not-human-ack | caregiver | Notification provider acceptance does not acknowledge incident | F12, F13 | 1. Advance simulated clock by 1300 seconds 2. {"action": "notify"} | 1. incidents where {"kind": "MISSING_MORNING_ACTIVITY", "state": "OPEN"} count = 1 2. notifications where {"state": "PROVIDER_ACCEPTED"} count >= 1 | Automated + Manual | v1.5.4 | PASS | Not Run
M047 | caregiver-lifecycle | caregiver | Claim acknowledge resolve closes incident and cancels pending routes | F12, F13 | 1. Advance simulated clock by 1300 seconds 2. {"as": "iid", "capture": "first_incident"} 3. {"action": "claim", "incident_id": "$iid"} 4. {"action": "acknowledge", "incident_id": "$iid"} 5. {"action": "resolve", "incident_id": "$iid"} | 1. incidents where {"state": "RESOLVED"} count = 1 2. notifications where {"state": "CANCELLED"} count = 2 | Automated + Manual | v1.5.4 | PASS | Not Run
M048 | settings-version-increments | configuration | Changing household policy creates a new config version | E07 | 1. Change household settings: {"door_open_timeout_seconds": 180} | 1. {"ge": 2, "path": "settings.config_version"} 2. settings.door_open_timeout_seconds = 180 | Automated + Manual | v1.5.4 | PASS | Not Run
M049 | invalid-privacy-event-rejected | negative | User-facing privacy event is not accepted by simulator controls | F02 | 1. Inject PRIVACY_ON from room1 |  | Automated + Manual | v1.5.4 | PASS | Not Run
M050 | invalid-kitchen-door-event-rejected | negative | Sensor capability mismatch is rejected | E07 | 1. Inject DOOR_OPEN from kitchen |  | Automated + Manual | v1.5.4 | PASS | Not Run
M051 | invalid-entry-ok-event-rejected | negative | Resident button event cannot be injected through door sensor | E07 | 1. Inject OK_PRESSED from entry |  | Automated + Manual | v1.5.4 | PASS | Not Run
M052 | invalid-advance-rejected | negative | Negative simulated time advance is rejected | NFR-08 | 1. Advance simulated clock by -1 seconds |  | Automated + Manual | v1.5.4 | PASS | Not Run
M053 | invalid-local-time-rejected | negative | Invalid local minute is rejected | E06 | 1. Set local minute to 1440 |  | Automated + Manual | v1.5.4 | PASS | Not Run
M054 | invalid-mode-rejected | negative | Unsupported mode is rejected | F10 | 1. Set home mode to PRIVACY |  | Automated + Manual | v1.5.4 | PASS | Not Run
M055 | invalid-door-timeout-rejected | negative | Unsafe door timeout setting is rejected | E07 | 1. Change household settings: {"door_open_timeout_seconds": 20} |  | Automated + Manual | v1.5.4 | PASS | Not Run
M056 | invalid-inactivity-threshold-rejected | negative | Unsafe inactivity threshold is rejected | E07 | 1. Change household settings: {"daytime_inactivity_seconds": 200} |  | Automated + Manual | v1.5.4 | PASS | Not Run
M057 | unknown-node-rejected | negative | Unknown node cannot inject sensor data | E07 | 1. Inject MOTION from garage |  | Automated + Manual | v1.5.4 | PASS | Not Run
M058 | node-fault-low_battery | diagnostics | Node fault LOW_BATTERY maps to stable diagnostics | E01, E10 | 1. Inject LOW_BATTERY on None 2. Run Troubleshoot on None | 1. devices where {"active": true, "code": "GS-N001", "health": "DEGRADED", "id": "kitchen"} count = 1 | Automated + Manual | v1.5.4 | PASS | Not Run
M059 | node-fault-battery_depleted | diagnostics | Node fault BATTERY_DEPLETED maps to stable diagnostics | E01, E10 | 1. Inject BATTERY_DEPLETED on None 2. Run Troubleshoot on None | 1. devices where {"active": false, "code": "GS-N002", "health": "OFFLINE", "id": "kitchen"} count = 1 | Automated + Manual | v1.5.4 | PASS | Not Run
M060 | node-fault-link_loss | diagnostics | Node fault LINK_LOSS maps to stable diagnostics and reboot recovery | E01, E10 | 1. Inject LINK_LOSS on None 2. Run Troubleshoot on None 3. Run Reboot on None | 1. devices where {"active": true, "code": "GS-OK000", "health": "ACTIVE", "id": "kitchen"} count = 1 | Automated + Manual | v1.5.4 | PASS | Not Run
M061 | node-fault-sensor_fault | diagnostics | Node fault SENSOR_FAULT maps to stable diagnostics | E01, E10 | 1. Inject SENSOR_FAULT on None 2. Run Troubleshoot on None | 1. devices where {"active": true, "code": "GS-N004", "health": "DEGRADED", "id": "kitchen"} count = 1 | Automated + Manual | v1.5.4 | PASS | Not Run
M062 | node-fault-over_temp | diagnostics | Node fault OVER_TEMP maps to stable diagnostics | E01, E10 | 1. Inject OVER_TEMP on None 2. Run Troubleshoot on None | 1. devices where {"active": false, "code": "GS-N005", "health": "OFFLINE", "id": "kitchen"} count = 1 | Automated + Manual | v1.5.4 | PASS | Not Run
M063 | node-fault-watchdog | diagnostics | Node fault WATCHDOG maps to stable diagnostics and reboot recovery | E01, E10 | 1. Inject WATCHDOG on None 2. Run Troubleshoot on None 3. Run Reboot on None | 1. devices where {"active": true, "code": "GS-OK000", "health": "ACTIVE", "id": "kitchen"} count = 1 | Automated + Manual | v1.5.4 | PASS | Not Run
M064 | hub-fault-power_loss | diagnostics | Hub fault POWER_LOSS maps to stable diagnostics | E04, E10 | 1. Inject POWER_LOSS on None 2. Run Troubleshoot on None | 1. devices where {"active": false, "code": "GS-H001", "health": "OFFLINE", "id": "hub"} count = 1 | Automated + Manual | v1.5.4 | PASS | Not Run
M065 | hub-fault-node_radio_failure | diagnostics | Hub fault NODE_RADIO_FAILURE maps to stable diagnostics and reboot recovery | E04, E10 | 1. Inject NODE_RADIO_FAILURE on None 2. Run Troubleshoot on None 3. Run Reboot on None | 1. devices where {"active": true, "code": "GS-OK000", "health": "ACTIVE", "id": "hub"} count = 1 | Automated + Manual | v1.5.4 | PASS | Not Run
M066 | hub-fault-internet_loss | diagnostics | Hub fault INTERNET_LOSS maps to stable diagnostics | E04, E10 | 1. Inject INTERNET_LOSS on None 2. Run Troubleshoot on None | 1. devices where {"active": true, "code": "GS-H003", "health": "DEGRADED", "id": "hub"} count = 1 | Automated + Manual | v1.5.4 | PASS | Not Run
M067 | hub-fault-over_temp | diagnostics | Hub fault OVER_TEMP maps to stable diagnostics | E04, E10 | 1. Inject OVER_TEMP on None 2. Run Troubleshoot on None | 1. devices where {"active": false, "code": "GS-H004", "health": "OFFLINE", "id": "hub"} count = 1 | Automated + Manual | v1.5.4 | PASS | Not Run
M068 | hub-fault-watchdog | diagnostics | Hub fault WATCHDOG maps to stable diagnostics and reboot recovery | E04, E10 | 1. Inject WATCHDOG on None 2. Run Troubleshoot on None 3. Run Reboot on None | 1. devices where {"active": true, "code": "GS-OK000", "health": "ACTIVE", "id": "hub"} count = 1 | Automated + Manual | v1.5.4 | PASS | Not Run

## Dummy Streams
Test ID | Fixture | Scenario | Steps | Expected / Assertions | Automation | Release | Current Status | Manual Result | Notes
DS001 | daytime_inactivity.json | Configured daytime inactivity triggers family check-in workflow | 1. Change household settings: {"daytime_inactivity_seconds": 300} 2. Set local minute to 600 3. Advance simulated clock by 300 seconds | 1. timeline where {"kind": "DAYTIME_INACTIVITY", "tone": "danger"} count = 1 2. incidents where {"kind": "DAYTIME_INACTIVITY", "state": "OPEN"} count = 1 | Automated replay | v1.5.4 | PASS | Not Run
DS002 | late_night_door.json | Late-night door stays open then closes | 1. Inject DOOR_OPEN from entry (late-night) 2. Advance simulated clock by 360 seconds 3. Inject DOOR_CLOSED from entry | 1. timeline where {"kind": "DOOR_LEFT_OPEN", "tone": "danger"} count = 1 2. home.latest_activity.kind = DOOR_CLOSED 3. home.latest_activity.details.resolved_left_open = True | Automated replay | v1.5.4 | PASS | Not Run
DS003 | missing_then_recovery_activity.json | Missing morning followed by later household activity | 1. Advance simulated clock by 1300 seconds 2. Inject MOTION from room1 3. Advance simulated clock by 120 seconds 4. Inject MOTION from kitchen 5. Inject DOOR_OPEN from entry | 1. incidents where {"kind": "MISSING_MORNING_ACTIVITY"} count = 1 2. home.recent_events where {"kind": "MOTION"} count >= 2 3. home.recent_events where {"kind": "DOOR_OPEN"} count = 1 | Automated replay | v1.5.4 | PASS | Not Run
DS004 | normal_morning.json | Normal morning kitchen and pooja activity | 1. Inject MOTION from kitchen 2. Advance simulated clock by 120 seconds 3. Inject MOTION from pooja 4. Advance simulated clock by 1180 seconds | 1. incidents where {"kind": "MISSING_MORNING_ACTIVITY"} count = 0 2. simulation.reason = evidence_present | Automated replay | v1.5.4 | PASS | Not Run
DS005 | offline_replay.json | Sensor activity during WAN loss is replayed after reconnect | 1. Set WAN disabled 2. Inject MOTION from kitchen 3. Advance simulated clock by 120 seconds 4. Set WAN enabled | 1. timeline where {"kind": "MOTION"} count = 1 2. simulation.pending_cloud = 0 | Automated replay | v1.5.4 | PASS | Not Run

## Requirement Coverage
Requirement | Automated Evidence | Manual Evidence | Hardware Pending | Coverage Status | Owner | Notes
F01 | tests/python/test_backend.py tests/js/app.test.mjs |  |  | Mapped
F02 | tests/python/test_backend.py tests/functional/scenario_catalog.json |  |  | Mapped
F03 | tests/js/app.test.mjs |  | identity/capability/radio/input installed-home drill | Mapped
F04 | tests/js/app.test.mjs tests/functional/scenario_catalog.json |  |  | Mapped
F05 | tests/cpp/test_main.cpp tests/functional/scenario_catalog.json |  |  | Mapped
F06 | tests/functional/scenario_catalog.json tests/simulation_http_test.py |  |  | Mapped
F07 | tests/python/test_backend.py tests/functional/scenario_catalog.json |  |  | Mapped
F08 | tests/cpp/test_main.cpp tests/functional/scenario_catalog.json tests/simulation_http_test.py |  |  | Mapped
F09 | tests/cpp/test_main.cpp tests/functional/scenario_catalog.json tests/simulation_http_test.py |  |  | Mapped
F10 | tests/functional/scenario_catalog.json |  |  | Mapped
F11 | tests/js/app.test.mjs tests/functional/scenario_catalog.json | tests/MANUAL_FUNCTIONAL_VALIDATION.md |  | Mapped
F12 | tests/functional/scenario_catalog.json tests/simulation_http_test.py |  |  | Mapped
F13 | tests/python/test_backend.py tests/functional/scenario_catalog.json |  |  | Mapped
F14 | tests/python/test_backend.py |  |  | Mapped
E01 | tests/functional/scenario_catalog.json |  |  | Mapped
E02 | tests/cpp/test_main.cpp tests/functional/scenario_catalog.json |  |  | Mapped
E03 | tests/functional/scenario_catalog.json tests/simulation_http_test.py |  |  | Mapped
E04 | tests/python/test_backend.py tests/simulation_http_test.py |  |  | Mapped
E05 | tests/python/test_database_schema.py |  | actual flash persistence/power-loss | Mapped
E06 | tests/cpp/test_main.cpp tests/functional/scenario_catalog.json |  |  | Mapped
E07 | tests/js/app.test.mjs tests/functional/scenario_catalog.json tests/simulation_http_test.py |  |  | Mapped
E08 | tests/python/test_backend.py tests/simulation_http_test.py |  |  | Mapped
E09 | tests/cpp/test_main.cpp |  | signed OTA/rollback/watchdog on target boards | Mapped
E10 | tests/python/test_logging.py tests/functional/scenario_catalog.json | tests/MANUAL_FUNCTIONAL_VALIDATION.md |  | Mapped

## Release Gate
Stage | Status | Evidence | Mandatory | Command / Notes | Release
validation coverage | PASS | 24/24 P0 IDs mapped | Yes | python scripts/check_validation_coverage.py | v1.5.4
contracts | PASS | 4 schemas + protocol examples + config + OpenAPI | Yes | python scripts/verify_contracts.py | v1.5.4
C++ unit/component | PASS | 80 checks | Yes | make cpp-test | v1.5.4
Python backend/database/logging/framework | PASS | 24 tests | Yes | make python-test | v1.5.4
JavaScript app | PASS | 10 tests | Yes | make app-test | v1.5.4
Base product profile | PASS | passed | Yes | make product-test PRODUCT=base | v1.5.4
AI product profile | PASS | passed | Yes | make product-test PRODUCT=ai | v1.5.4
feature flag matrix | PASS | 4/4 variants | Yes | 4 simulator builds / feature variants | v1.5.4
dummy sensor streams | PASS | 5/5 streams | Yes | python tools/validation/run_dummy_sensor_streams.py | v1.5.4
connected functional catalog | PASS | 68/68 scenarios | Yes | python tools/validation/run_functional_suite.py | v1.5.4
HTTP integration | PASS | 16/16 tests | Yes | python tests/simulation_http_test.py | v1.5.4
ASan/UBSan | PASS | 80 C++ checks | Yes | make verify-sanitize | v1.5.4
trace-enabled C++ | PASS | 80 checks | Yes | make cpp-test TRACE_FLAGS=-DGS_ENABLE_TRACE=1 | v1.5.4
Playwright browser | MANUAL_REQUIRED | Playwright not installed; generated manual plan provided | Browser-specific | node tests/simulation_browser_test.cjs / make release-gate-browser | v1.5.4

## Manual UI Checks
Check ID | Manual Visual / Usability Check | Expected | Result | Defect ID | Evidence / Screenshot | Notes
UI001 | I am OK is visually positive/green and includes elapsed time | Requirement satisfied in browser/PWA | Not Run
UI002 | Unexpected/concern events are visually distinct and are not communicated by color alone | Requirement satisfied in browser/PWA | Not Run
UI003 | Active/degraded/offline device states have text labels as well as colored status circles | Requirement satisfied in browser/PWA | Not Run
UI004 | 390 px mobile viewport has no horizontal overflow and primary controls remain usable | Requirement satisfied in browser/PWA | Not Run
UI005 | Family/caregiver timeline is newest-first and unresolved missing-morning/call incidents remain visible | Requirement satisfied in browser/PWA | Not Run
UI006 | Settings values reload after Save and display the new configuration version | Requirement satisfied in browser/PWA | Not Run
UI007 | No Privacy ON/OFF control is present in normal household Settings | Requirement satisfied in browser/PWA | Not Run

## Untested & HIL
Gap ID | Area | Gate Type | What is untested / must be validated | Target Gate | Current Status | Owner | Target Release | Evidence / Notes
HIL-001 | Real PIR/reed/buttons | Hardware/HIL | Debounce, stuck input, electrical noise, mounting, field wiring, button response latency | Mandatory before unattended pilot | PENDING
HIL-002 | ESP-NOW RF/RSSI/offline timing | Hardware/HIL | Real packet loss, channel coexistence/interference/range, RSSI distribution, missed heartbeats and reconnect | Mandatory before unattended pilot | PENDING
HIL-003 | Battery/runtime/charging/UPS | Hardware/HIL | ADC calibration, runtime, charge behavior, brown-out under load, UPS handover, low-battery thresholds | Mandatory before unattended pilot | PENDING
HIL-004 | Brown-out/reset/watchdog | Hardware/HIL | Actual reset reasons, reboot recovery, watchdog behavior and persistent state on target boards | Mandatory before unattended pilot | PENDING
HIL-005 | Flash persistence/wear | Hardware/HIL | Power-loss atomicity, queue retention, compaction, overflow, wear and durable recovery | Mandatory before unattended pilot | PENDING
HIL-006 | OTA signing/rollback | Hardware/HIL | Real signature/hash, wrong-board image, interrupted update, rollback and first-boot recovery | Mandatory before unattended pilot | PENDING
HIL-007 | Temperature telemetry | Hardware/HIL | Real sensor/MCU temperature thresholds and false-positive behavior | Mandatory before unattended pilot | PENDING
HIL-008 | Real notification provider | External integration | Provider failure/timeout/receipt, duplicate delivery, phone receipt/background restrictions/retry | Mandatory before unattended pilot | PENDING
HIL-009 | Installed-home coverage | Pilot/HIL | Room placement, dead zones, sensor line-of-sight, router/power conditions, full routine-window coverage | Mandatory before unattended pilot | PENDING
GAP-001 | Long-duration soak | Recommended gap | 24 h / 72 h / multi-week repeated events, retries and storage pressure | Recommended before pilot | NOT EXHAUSTIVE
GAP-002 | High-rate bursts and queue saturation | Recommended gap | Realistic FreeRTOS scheduling, queue pressure and event bursts on exact ESP32 variants | Recommended before pilot | NOT EXHAUSTIVE
GAP-003 | Network jitter/reordering/partial loss | Recommended gap | Multi-boundary jitter, reordering and loss beyond deterministic modeled cases | Recommended before pilot | NOT EXHAUSTIVE
GAP-004 | Production security/penetration | Recommended gap | TLS, production authN/authZ, credential rotation/revocation, endpoint and log review | Mandatory before production | NOT EXHAUSTIVE
GAP-005 | Target resource/performance budgets | Recommended gap | CPU, RAM, flash, wake time, Wi-Fi/ESP-NOW coexistence and battery current | Mandatory before pilot | NOT EXHAUSTIVE
GAP-006 | Accessibility/usability on target devices | Recommended gap | Target caregivers/residents, Android/browser matrix and accessibility comprehension | Recommended before pilot | NOT EXHAUSTIVE
GAP-007 | Persistent backend DB operations | Recommended gap | Concurrency, crash consistency, migrations, upgrade/rollback, backup/restore | Before production backend | NOT EXHAUSTIVE
GAP-008 | Timezone/DST exhaustive coverage | Recommended gap | Non-India deployments, DST transitions, clock rollback/uncertainty boundaries | Before non-India rollout | NOT EXHAUSTIVE

## Diagnostic Matrix
Test ID | Device | Fault | Expected Health | Expected Active | Error Code | Recovery Expected | Current Status
M058 |  | LOW_BATTERY | DEGRADED | TRUE | GS-N001 | No | PASS
M059 |  | BATTERY_DEPLETED | OFFLINE | FALSE | GS-N002 | No | PASS
M060 |  | LINK_LOSS | ACTIVE | TRUE | GS-OK000 | Yes | PASS
M061 |  | SENSOR_FAULT | DEGRADED | TRUE | GS-N004 | No | PASS
M062 |  | OVER_TEMP | OFFLINE | FALSE | GS-N005 | No | PASS
M063 |  | WATCHDOG | ACTIVE | TRUE | GS-OK000 | Yes | PASS
M064 |  | POWER_LOSS | OFFLINE | FALSE | GS-H001 | No | PASS
M065 |  | NODE_RADIO_FAILURE | ACTIVE | TRUE | GS-OK000 | Yes | PASS
M066 |  | INTERNET_LOSS | DEGRADED | TRUE | GS-H003 | No | PASS
M067 |  | OVER_TEMP | OFFLINE | FALSE | GS-H004 | No | PASS
M068 |  | WATCHDOG | ACTIVE | TRUE | GS-OK000 | Yes | PASS